## Feature Inventory
Category | Subcategory | Feature/Component | Description | Location | Priority | Notes | Implementation Time | Current Status %
Authentication | Login Flow | JWT Token Generation | POST /api/auth/login returns JWT token on valid credentials | Admin Backend | P0
Authentication | Login Flow | Login Form UI | Email/password form with validation | Admin Frontend | P0
Authentication | Login Flow | Token Storage | JWT stored in localStorage with expiration tracking | Admin Frontend | P0
Authentication | Login Flow | Auto-redirect on Login | Redirect to dashboard after successful login | Admin Frontend | P0
Authentication | Logout | Token Removal | Clear JWT from storage on logout | Admin Frontend | P0
Authentication | Logout | Redirect to Login | Navigate to login page after logout | Admin Frontend | P0
Authentication | Session | Token Expiration Check | Validate token expiration before API calls | Admin Frontend | P0
Authentication | Session | Auto-logout on 401 | Automatically logout when API returns 401 | Admin Frontend | P0
Authentication | Session | Get Current User | GET /api/auth/me returns current user info | Admin Backend | P0
Authentication | Password | Bcrypt Hashing | Passwords hashed with bcrypt before storage | Admin Backend | P0
Authentication | Password | Password Reset | Allow users to reset password | Admin Backend | P2 | Not implemented - requires email service
Authorization | Roles | Admin Role | Full access to all features | Admin Backend | P0
Authorization | Roles | Editor Role | Create/update POIs, manage images, no delete | Admin Backend | P0
Authorization | Roles | Viewer Role | Read-only access to all data | Admin Backend | P0
Authorization | Permissions | Permission Decorator | require_permission() decorator on endpoints | Admin Backend | P0
Authorization | Permissions | Frontend Role Check | useAuth() hook for permission checks | Admin Frontend | P0
Authorization | Permissions | Protected Routes | Routes require authentication to access | Admin Frontend | P0
POI Management | Create | Create POI Endpoint | POST /api/pois/ creates new POI | Admin Backend | P0
POI Management | Create | Create POI Form | Multi-section accordion form for POI creation | Admin Frontend | P0
POI Management | Create | Type Selection | Select POI type (Business, Park, Trail, Event, etc.) | Admin Frontend | P0
POI Management | Create | Auto-save | Automatically save form changes | Admin Frontend | P1
POI Management | Read | Get POI by ID | GET /api/pois/{id} returns POI details | Admin Backend | P0
POI Management | Read | Get POI by Slug | GET /api/pois/by-slug/{slug} returns POI | App Backend | P0
POI Management | Read | List POIs (Admin) | GET /api/admin/pois/ includes drafts | Admin Backend | P0
POI Management | Read | List POIs (Public) | GET /api/pois/ only published POIs | App Backend | P0
POI Management | Read | POI List Table | Sortable, searchable table of all POIs | Admin Frontend | P0
POI Management | Update | Update POI Endpoint | PUT /api/pois/{id} updates POI | Admin Backend | P0 | NN-55: HTTP 422 errors reported
POI Management | Update | Update POI Form | Pre-populated form with existing data | Admin Frontend | P0
POI Management | Update | Partial Updates | Only send changed fields | Admin Frontend | P1
POI Management | Delete | Delete POI Endpoint | DELETE /api/pois/{id} removes POI | Admin Backend | P0
POI Management | Delete | Delete Confirmation | Confirm dialog before deletion | Admin Frontend | P0
POI Management | Publication | Draft Status | POIs created as drafts by default | Admin Backend | P0
POI Management | Publication | Publish POI | Change status from draft to published | Admin Backend | P0
POI Management | Publication | Publication Filter | Public endpoints filter by published only | App Backend | P0
POI Management | Publication | Status Badge | Show draft/published status in admin list | Admin Frontend | P0
POI Management | Slugs | Auto-generate Slug | Generate slug from name + city | Admin Backend | P0
POI Management | Slugs | Unique Slug Enforcement | Append number if slug exists | Admin Backend | P0
POI Management | Slugs | SEO-friendly URLs | Use slugs in public URLs | App Frontend | P0
POI Types | Business | Business Subtype Table | Separate table for business-specific fields | Database | P0
POI Types | Business | Price Range | price_range field (e.g., $, $$, $$$) | Admin Backend | P0
POI Types | Business | Business Hours | Regular operating hours | Admin Backend | P0
POI Types | Business | Business Amenities | WiFi, parking, restrooms, etc. | Admin Backend | P0
POI Types | Business | Business Detail Page | BusinessDetail.jsx component | App Frontend | P0 | NN-39: Design implementation needed
POI Types | Business | Key Facilities Display | Show restrooms, wheelchair, WiFi, pet-friendly | App Frontend | P0 | NN-49: Add to businesses
POI Types | Park | Park Subtype Table | Separate table for park-specific fields | Database | P0
POI Types | Park | Drone Policy | drones_allowed field | Admin Backend | P1
POI Types | Park | Park Facilities | Playgrounds, pavilions, trails | Admin Backend | P0
POI Types | Park | Natural Features | Lakes, forests, fields | Admin Backend | P1
POI Types | Park | Park Detail Page | ParkDetail.jsx component | App Frontend | P0 | NN-41: Design implementation needed
POI Types | Park | Playground Info | Playground type, surface, notes | Admin Backend | P0 | NN-57: Missing lat/long for playgrounds
POI Types | Park | Playground Duplicates | Add multiple playgrounds per park | Admin Backend | P1 | NN-57: Need duplicate button
POI Types | Trail | Trail Subtype Table | Separate table for trail-specific fields | Database | P0
POI Types | Trail | Trail Length | length_miles field | Admin Backend | P0
POI Types | Trail | Trail Difficulty | Easy, Moderate, Hard | Admin Backend | P0
POI Types | Trail | Route Type | Loop, out-and-back, point-to-point | Admin Backend | P0
POI Types | Trail | Surface Types | Dirt, gravel, asphalt, etc. | Admin Backend | P0
POI Types | Trail | Trailhead Coordinates | Lat/long for trail start | Admin Backend | P0
POI Types | Trail | Trail Exit Coordinates | Lat/long for trail end | Admin Backend | P0
POI Types | Trail | Trailhead Photos | Upload photos of trailhead | Admin Backend | P0 | NN-57: Need 10 images, currently 1
POI Types | Trail | Trail Exit Photos | Upload photos of trail exit | Admin Backend | P0 | NN-57: Need 10 images, currently 1
POI Types | Trail | Trail Detail Page | TrailDetail.jsx component | App Frontend | P0 | NN-42: Design implementation needed
POI Types | Trail | Downloadable Maps | PDF map uploads | Admin Backend | P1
POI Types | Event | Event Subtype Table | Separate table for event-specific fields | Database | P0
POI Types | Event | Start DateTime | Event start date and time | Admin Backend | P0
POI Types | Event | End DateTime | Event end date and time | Admin Backend | P0
POI Types | Event | Repeat Pattern | Recurring event pattern (weekly, monthly) | Admin Backend | P1
POI Types | Event | Organizer Info | Name, email, phone of organizer | Admin Backend | P0
POI Types | Event | Venue Selection | Link event to venue POI | Admin Backend | P0 | NN-46: Venue data inheritance
POI Types | Event | Venue Data Inheritance | Pull address, parking, etc. from venue | Admin Backend | P1 | NN-46: Not implemented
POI Types | Event | Ticket URL | Link to buy tickets | Admin Backend | P0
POI Types | Event | Is Free | Boolean flag for free events | Admin Backend | P0
POI Types | Event | Vendor Management | List of vendors at event | Admin Backend | P1
POI Types | Event | Event Detail Page | EventDetail.jsx component | App Frontend | P0 | NN-44: Design implementation needed
POI Types | Event | Past Event Exclusion | Hide events after end date in Nearby | App Backend | P0 | NN-30: Verify working
POI Types | Event | Events Page | List of all events | App Frontend | P0 | NN-46: Showing blank page
POI Types | Services | Services POI Type | Service provider listings | Admin Backend | P2
POI Types | Youth Activities | Youth Activities POI Type | Youth programs and activities | Admin Backend | P2
POI Types | Jobs | Jobs POI Type | Job listings | Admin Backend | P3
POI Types | Volunteer | Volunteer Opportunities Type | Volunteer positions | Admin Backend | P3
POI Types | Disaster Hubs | Disaster Hubs POI Type | Emergency resources | Admin Backend | P2
POI Form | Core Information | Name Field | POI name input | Admin Frontend | P0
POI Form | Core Information | Type Selection | POI type dropdown | Admin Frontend | P0
POI Form | Core Information | Teaser Paragraph | Short description (120 chars) | Admin Frontend | P0 | NN-57: Need character limit
POI Form | Core Information | Primary Type | Primary business type selection | Admin Frontend | P0
POI Form | Core Information | Listing Type | Free, Paid, Sponsor, etc. | Admin Frontend | P0
POI Form | Core Information | Lat/Long Accuracy Flag | Mark if coordinates are most accurate | Admin Frontend | P1 | NN-57: Need button to flag
POI Form | Location | Street Address | Street address input | Admin Frontend | P0
POI Form | Location | City | City input | Admin Frontend | P0 | NN-38: Suggest dropdown for Chatham County cities
POI Form | Location | State | State input | Admin Frontend | P0 | NN-38: Default to NC
POI Form | Location | Zip Code | Zip code input | Admin Frontend | P0
POI Form | Location | County | County input | Admin Frontend | P0 | NN-38: Default to Chatham
POI Form | Location | Coordinates Picker | Map click to set lat/long | Admin Frontend | P0
POI Form | Location | Map Zoom Level | Adjust default zoom for easier use | Admin Frontend | P1 | NN-38: Zoom too far out
POI Form | Location | Address Autocomplete | Suggest addresses as user types | Admin Frontend | P2 | NN-38: Not implemented
POI Form | Location | Front Door Coordinates | Separate lat/long for entrance | Admin Frontend | P0
POI Form | Parking | Parking Types | Multi-select parking options | Admin Frontend | P0
POI Form | Parking | Parking Notes | Text field for parking details | Admin Frontend | P0 | NN-57: Missing on free listings
POI Form | Parking | Parking Lat/Long | Coordinates for parking lot | Admin Frontend | P0 | NN-57: Missing
POI Form | Parking | Parking Photos | Upload parking area photos | Admin Frontend | P0 | NN-57: Need per-location photos
POI Form | Parking | Additional Parking | Add multiple parking locations | Admin Frontend | P1 | NN-57: Goes to white screen
POI Form | Parking | Public Transit Info | Transit access details | Admin Frontend | P1 | NN-57: Missing on free listings
POI Form | Parking | Expect to Pay | Parking fee indicator | Admin Frontend | P0 | NN-57: Missing on free listings
POI Form | Contact | Phone Number | Primary phone input | Admin Frontend | P0
POI Form | Contact | Email | Contact email input | Admin Frontend | P0
POI Form | Contact | Website | Website URL input | Admin Frontend | P0
POI Form | Social Media | Instagram | Instagram handle/URL | Admin Frontend | P0
POI Form | Social Media | Facebook | Facebook page URL | Admin Frontend | P0
POI Form | Social Media | X/Twitter | Twitter/X handle | Admin Frontend | P0
POI Form | Social Media | TikTok | TikTok handle | Admin Frontend | P1
POI Form | Social Media | LinkedIn | LinkedIn page URL | Admin Frontend | P1
POI Form | Categories | Main Category Selector | Select primary category (required) | Admin Frontend | P0
POI Form | Categories | Secondary Categories | Select additional categories | Admin Frontend | P0
POI Form | Categories | Category Tree Display | Hierarchical category picker | Admin Frontend | P0
POI Form | Categories | Type-filtered Categories | Only show categories for POI type | Admin Frontend | P0
POI Form | Categories | Business Category Limit | Limit to 1 category for free business | Admin Frontend | P0 | NN-57: Currently unlimited
POI Form | Hours | Regular Hours Input | Day-by-day hours picker | Admin Frontend | P0
POI Form | Hours | Seasonal Hours | Hours for specific seasons | Admin Frontend | P1 | NN-36: Missing date range
POI Form | Hours | Holiday Hours | Special holiday hours | Admin Frontend | P1
POI Form | Hours | Recurring Exceptions | Monthly exceptions (3rd Wed closed) | Admin Frontend | P2 | NN-36: Not implemented
POI Form | Facilities | Public Restrooms Toggle | Are restrooms available? | Admin Frontend | P0
POI Form | Facilities | Restroom Options | Restroom type checkboxes | Admin Frontend | P0
POI Form | Facilities | Restroom Description | Text field for restroom details | Admin Frontend | P0 | NN-57: Missing
POI Form | Facilities | Restroom Lat/Long | Coordinates for restroom location | Admin Frontend | P0 | NN-57: Missing
POI Form | Facilities | Restroom Photos | Upload restroom photos | Admin Frontend | P0 | NN-57: Missing
POI Form | Facilities | Add Another Restroom | Duplicate restroom section | Admin Frontend | P1 | NN-57: Need duplicate button
POI Form | Facilities | Wheelchair Accessible | Yes/No/Unknown selector | Admin Frontend | P0
POI Form | Facilities | Accessibility Details | Text field for details | Admin Frontend | P0
POI Form | Facilities | WiFi Available | Free WiFi checkbox | Admin Frontend | P0
POI Form | Facilities | Pet Policy | Pet-friendly options | Admin Frontend | P0
POI Form | Facilities | Alcohol Available | Yes/No selector | Admin Frontend | P0
POI Form | Facilities | Alcohol Policy Details | Text for alcohol policy | Admin Frontend | P0 | NN-57: Missing
POI Form | Outdoor Features | Drone Usage Policy | Drone rules text field | Admin Frontend | P1
POI Form | Outdoor Features | Fishing Info | Fishing availability and details | Admin Frontend | P1
POI Form | Outdoor Features | Hunting Info | Hunting availability and details | Admin Frontend | P1
POI Form | Rentals | Rentals Available | Toggle for rental availability | Admin Frontend | P1
POI Form | Rentals | Rental Description | Text field for rental details | Admin Frontend | P1
POI Form | Rentals | Rental Link | URL for booking | Admin Frontend | P1
POI Form | Rentals | Rental Photos | Upload rental item photos | Admin Frontend | P1 | NN-57: Missing
POI Form | Rentals | Rental Pricing Box | Pricing input section | Admin Frontend | P3 | NN-57: Remove - not used
POI Form | Community | Community Connections | Links to related content | Admin Frontend | P1
POI Form | Community | Article Links | Links with custom titles | Admin Frontend | P1 | NN-57: Need custom title field
POI Form | Community | Community Impact | Community involvement section | Admin Frontend | P2 | NN-57: Remove from free listings
POI Form | Corporate | Comments Restrictions | Restrictions on public comments | Admin Frontend | P2 | NN-57: Checkbox not clickable
POI Form | Corporate | Social Media Restrictions | Platforms that can't be used | Admin Frontend | P2 | NN-57: Checkbox not clickable
POI Form | Corporate | Pre-approval Required | Approval before featuring | Admin Frontend | P2 | NN-57: Checkbox not clickable
POI Form | Corporate | Branding Requirements | Required/avoided language | Admin Frontend | P2 | NN-57: Checkbox not clickable
POI Form | Misc | Long Description | Rich text editor for full description | Admin Frontend | P0
POI Form | Misc | Internal Notes | Admin-only notes | Admin Frontend | P1
POI Form | Misc | History Paragraph | Historical information | Admin Frontend | P2
POI Form | Misc | Verified Flag | Mark as verified by team | Admin Frontend | P0
POI Form | Misc | Disaster Hub Flag | Mark as disaster resource | Admin Frontend | P2
Categories | Structure | Hierarchical Tree | Categories with parent-child relationships | Database | P0
Categories | Structure | Unlimited Nesting | Any depth of category nesting | Admin Backend | P0
Categories | Structure | POI Type Filtering | applicable_types array per category | Admin Backend | P0
Categories | Structure | Slug Generation | Auto-generate category slugs | Admin Backend | P0
Categories | API | Get Category Tree | GET /api/categories/tree endpoint | Admin Backend | P0
Categories | API | Get by POI Type | GET /api/categories/by-poi-type/{type} | Admin Backend | P0
Categories | API | Create Category | POST /api/categories/ endpoint | Admin Backend | P0
Categories | API | Update Category | PUT /api/categories/{id} endpoint | Admin Backend | P0
Categories | API | Delete Category | DELETE /api/categories/{id} endpoint | Admin Backend | P0
Categories | API | Circular Reference Prevention | Prevent category from being its own parent | Admin Backend | P0
Categories | Frontend | Category List Page | Admin page showing all categories | Admin Frontend | P0
Categories | Frontend | Category Selector | Hierarchical picker in POI form | Admin Frontend | P0
Categories | Frontend | Main Category Badge | Indicate main vs secondary | Admin Frontend | P0
Images | Storage | S3 Storage | Store images in AWS S3 | Admin Backend | P0
Images | Storage | MinIO (Dev) | S3-compatible local storage | Infrastructure | P0
Images | Storage | Database Storage Deprecated | No longer store binary in DB | Admin Backend | P0
Images | Types | Main Image | Primary featured image | Admin Backend | P0
Images | Types | Gallery Images | Additional photo gallery | Admin Backend | P0
Images | Types | Entry Photos | Entrance/storefront photos | Admin Backend | P0
Images | Types | Parking Photos | Parking area photos | Admin Backend | P0
Images | Types | Restroom Photos | Restroom photos | Admin Backend | P0
Images | Types | Rental Photos | Rental equipment photos | Admin Backend | P1
Images | Types | Playground Photos | Playground photos | Admin Backend | P1
Images | Types | Menu Photos | Menu images | Admin Backend | P0
Images | Types | Trail Head Photos | Trailhead location photos | Admin Backend | P0
Images | Types | Trail Exit Photos | Trail exit location photos | Admin Backend | P0
Images | Types | Map Images | Map graphics | Admin Backend | P1
Images | Types | Downloadable Maps | PDF maps (20MB max) | Admin Backend | P1
Images | Variants | Original Size | Full resolution upload | Admin Backend | P0
Images | Variants | XLarge (1920x1080) | Hero image size | Admin Backend | P0
Images | Variants | Large (1200x800) | Detail page size | Admin Backend | P0
Images | Variants | Medium (600x400) | Card/list size | Admin Backend | P0
Images | Variants | Thumbnail (200x200) | Grid preview size | Admin Backend | P0
Images | Variants | Auto-generation | Create variants on upload | Admin Backend | P0
Images | Upload | Single Upload | POST /api/images/upload/{poi_id} | Admin Backend | P0
Images | Upload | Bulk Upload | POST /api/images/bulk-upload/{poi_id} | Admin Backend | P0
Images | Upload | Drag-and-Drop | Drag files to upload | Admin Frontend | P0
Images | Upload | File Size Limit | 10MB max (20MB for PDFs) | Admin Backend | P0
Images | Upload | Format Validation | JPEG, PNG, WebP, PDF only | Admin Backend | P0
Images | Management | Reorder Images | Drag to reorder gallery | Admin Frontend | P0
Images | Management | Alt Text | Add alt text for accessibility | Admin Frontend | P0
Images | Management | Captions | Add captions to images | Admin Frontend | P1
Images | Management | Delete Image | Remove image from POI | Admin Frontend | P0
Attributes | Types | Text Attribute | Single line text input | Admin Backend | P0
Attributes | Types | Textarea Attribute | Multi-line text input | Admin Backend | P0
Attributes | Types | Number Attribute | Numeric input with min/max | Admin Backend | P0
Attributes | Types | Select Attribute | Single choice dropdown | Admin Backend | P0
Attributes | Types | Multi-select Attribute | Multiple choice checkboxes | Admin Backend | P0
Attributes | Types | Checkbox Attribute | Boolean toggle | Admin Backend | P0
Attributes | Types | Date Attribute | Date picker input | Admin Backend | P0
Attributes | Types | Time Attribute | Time picker input | Admin Backend | P0
Attributes | Types | URL Attribute | URL input with validation | Admin Backend | P0
Attributes | Types | Email Attribute | Email input with validation | Admin Backend | P0
Attributes | Config | POI Type Filtering | Limit attributes to POI types | Admin Backend | P0
Attributes | Config | Required Flag | Mark attribute as required | Admin Backend | P0
Attributes | Config | Default Value | Set default value | Admin Backend | P1
Attributes | Config | Help Text | Display help text to users | Admin Backend | P1
Attributes | Config | Display Order | Control attribute order | Admin Backend | P1
Attributes | Frontend | Dynamic Form Rendering | Render attributes based on config | Admin Frontend | P0
Attributes | Frontend | Validation | Client-side validation per type | Admin Frontend | P0
Relationships | Types | Event-Venue | Link event to venue location | Admin Backend | P0
Relationships | Types | Event-Vendor | Link event to vendor businesses | Admin Backend | P1
Relationships | Types | Event-Sponsor | Link event to sponsors | Admin Backend | P2
Relationships | Types | Trail-in-Park | Link trail to containing park | Admin Backend | P0
Relationships | Types | Service Provider | Link service to POI | Admin Backend | P2
Relationships | Types | Related POIs | Generic relation between POIs | Admin Backend | P1
Relationships | API | Create Relationship | POST /api/relationships/ | Admin Backend | P0
Relationships | API | Get POI Relationships | GET /api/relationships/{poi_id} | Admin Backend | P0
Relationships | API | Delete Relationship | DELETE /api/relationships/... | Admin Backend | P0
Relationships | Frontend | Relationship Manager | UI to add/remove relationships | Admin Frontend | P0
Relationships | Frontend | POI Search for Linking | Search POIs to create link | Admin Frontend | P0
Relationships | Frontend | Display Relationships | Show linked POIs on detail page | App Frontend | P1 | NN-40: Not implemented
Search | Keyword | pg_trgm Fuzzy Search | Trigram-based fuzzy matching | App Backend | P0
Search | Keyword | Search Endpoint | GET /api/pois/search?q=... | App Backend | P0
Search | Keyword | Similarity Threshold | 0.3 minimum similarity | App Backend | P0
Search | Keyword | Name Weighting | Name matches weighted 2x | App Backend | P0
Search | Semantic | Embedding Model | michaelfeil/embeddinggemma-300m (~1GB) | App Backend | P0
Search | Semantic | Vector Storage | pgvector extension for embeddings | Database | P0
Search | Semantic | Semantic Endpoint | GET /api/pois/semantic-search?q=... | App Backend | P0
Search | Semantic | Natural Language | Understand queries like 'dog friendly cafe' | App Backend | P0
Search | Semantic | Fallback to Keyword | Use keyword if embeddings unavailable | App Backend | P0
Search | Hybrid | Combined Search | 30% keyword + 70% semantic | App Backend | P0
Search | Hybrid | Configurable Weights | Adjust keyword/semantic balance | App Backend | P1
Search | Hybrid | Hybrid Endpoint | GET /api/pois/hybrid-search?q=... | App Backend | P0
Search | Frontend | Search Bar Component | SearchBar.jsx with input | App Frontend | P0
Search | Frontend | Debounced Input | 300ms delay before API call | App Frontend | P0
Search | Frontend | Search Dropdown | Results list with keyboard nav | App Frontend | P0
Search | Frontend | Keyboard Navigation | Arrow keys, Enter, Escape | App Frontend | P0
Search | Frontend | Result Highlighting | Highlight selected result | App Frontend | P0
Nearby | Core | Nearby API Endpoint | GET /api/pois/{poi_id}/nearby | App Backend | P0
Nearby | Core | Distance Calculation | PostGIS ST_DWithin/ST_Distance | App Backend | P0
Nearby | Core | Miles to Meters | Convert miles to meters for PostGIS | App Backend | P0
Nearby | Core | Sort by Distance | Return nearest first | App Backend | P0
Nearby | Filters | Radius Dropdown | 1, 3, 5, 10, 15 miles | App Frontend | P0
Nearby | Filters | Type Filter Pills | All, Businesses, Events, Parks, Trails | App Frontend | P0
Nearby | Filters | Youth Events Filter | Filter for youth activities | App Frontend | P1
Nearby | Filters | Date Presets | Today, Tomorrow, This Weekend | App Frontend | P0
Nearby | Filters | Custom Date Picker | Select specific date | App Frontend | P0
Nearby | Filters | Search Within Nearby | Hybrid search filtered to nearby | App Frontend | P0
Nearby | Filters | Clear Filters Button | Reset all filters | App Frontend | P0
Nearby | Map | Leaflet Map | Map showing nearby POIs | App Frontend | P0
Nearby | Map | Carto Voyager Tiles | Warm, MapQuest-like colors | App Frontend | P0 | NN-50: Accessibility concerns
Nearby | Map | Numbered Markers | Purple circles with numbers | App Frontend | P0
Nearby | Map | Current POI Marker | Gold/yellow circle for current | App Frontend | P0
Nearby | Map | Auto-fit Bounds | Zoom to show all markers | App Frontend | P0
Nearby | Map | Marker Click Highlight | Click marker to highlight card | App Frontend | P0
Nearby | Map | Card Click Pan | Click card to highlight marker | App Frontend | P0
Nearby | Cards | NearbyCard Component | Individual POI card in list | App Frontend | P0 | NN-33: Design update needed
Nearby | Cards | Distance Display | Show miles from current POI | App Frontend | P0
Nearby | Cards | Hours Display | Show hours for selected date | App Frontend | P0
Nearby | Cards | Category Display | Show primary category | App Frontend | P0
Nearby | Cards | Amenity Icons | Restrooms, wheelchair, WiFi, pets | App Frontend | P0
Nearby | Cards | Trail Info | Length and difficulty for trails | App Frontend | P0
Nearby | Cards | Event Info | Date for events | App Frontend | P0
Nearby | Cards | Park Info | Park type for parks | App Frontend | P0
Nearby | Actions | Directions Modal | Choose navigation app | App Frontend | P0 | NN-31: Styling updates
Nearby | Actions | Google Maps Link | Open in Google Maps | App Frontend | P0
Nearby | Actions | Apple Maps Link | Open in Apple Maps | App Frontend | P0
Nearby | Actions | Waze Link | Open in Waze | App Frontend | P0
Nearby | Actions | Copy Address | Copy address to clipboard | App Frontend | P0 | NN-31: Only copying city
Nearby | Actions | Copy Lat/Long | Copy coordinates to clipboard | App Frontend | P0
Nearby | Pagination | Page Navigation | Next/previous page buttons | App Frontend | P0
Nearby | Pagination | Items Per Page | 6 items per page default | App Frontend | P0
Nearby | Mobile | Touch Targets | 44px+ for accessibility | App Frontend | P0
Nearby | Mobile | Horizontal Scroll Pills | Swipe filter buttons | App Frontend | P0
Nearby | Mobile | Icon-only Mode | Icons without text on small screens | App Frontend | P0
Nearby | Mobile | Responsive Breakpoints | 768px, 480px, 360px | App Frontend | P0
Detail Pages | Routing | Smart Router | POIDetail.jsx dispatches to type-specific | App Frontend | P0
Detail Pages | Routing | Slug-based URLs | /places/, /parks/, /trails/, /events/ | App Frontend | P0
Detail Pages | Routing | UUID Fallback | /poi/{uuid} redirects to slug URL | App Frontend | P0
Detail Pages | Business | BusinessDetail Page | Full business detail view | App Frontend | P0 | NN-39: Design implementation
Detail Pages | Business | Price Range Display | $, $$, $$$ indicator | App Frontend | P0
Detail Pages | Business | Business Hours | Show weekly hours with toggle | App Frontend | P0 | NN-36: Toggle not working
Detail Pages | Business | Contact Info | Phone, email, website | App Frontend | P0
Detail Pages | Business | Social Links | Instagram, Facebook, X, etc. | App Frontend | P0
Detail Pages | Park | ParkDetail Page | Full park detail view | App Frontend | P0 | NN-41: Design implementation
Detail Pages | Park | Park Type Display | State park, local park, etc. | App Frontend | P0
Detail Pages | Park | Facilities List | Playgrounds, pavilions, etc. | App Frontend | P0
Detail Pages | Trail | TrailDetail Page | Full trail detail view | App Frontend | P0 | NN-42: Design implementation
Detail Pages | Trail | Length Display | Miles with icon | App Frontend | P0
Detail Pages | Trail | Difficulty Badge | Easy/Moderate/Hard | App Frontend | P0
Detail Pages | Trail | Surface Types | Dirt, gravel, paved, etc. | App Frontend | P0
Detail Pages | Event | EventDetail Page | Full event detail view | App Frontend | P0 | NN-44: Design implementation
Detail Pages | Event | Date/Time Display | Event date and time | App Frontend | P0
Detail Pages | Event | Status Indicator | Upcoming, happening now, past | App Frontend | P0
Detail Pages | Event | Organizer Info | Event organizer details | App Frontend | P0
Detail Pages | Event | Ticket Link | Button to buy tickets | App Frontend | P0
Detail Pages | Common | Photo Gallery | Display all POI images | App Frontend | P0
Detail Pages | Common | Photo Lightbox | Full-screen image viewer | App Frontend | P0
Detail Pages | Common | Directions Button | Open in maps app | App Frontend | P0
Detail Pages | Common | Share Button | Share via social/email | App Frontend | P0 | NN-38: Only showing copy link
Detail Pages | Common | Copy Lat/Long | Copy coordinates | App Frontend | P0 | NN-35: Was showing null
Detail Pages | Common | Verified Badge | Show verified status | App Frontend | P0 | NN-48: Popup not showing
Detail Pages | Common | Nearby Section | Embedded nearby feature | App Frontend | P0
Detail Pages | Common | Amenity Display | Icons for facilities | App Frontend | P0
Maps | Library | React-Leaflet | Leaflet wrapper for React | App Frontend | P0
Maps | Tiles | Carto Voyager | Warm, colorful map tiles | App Frontend | P0 | NN-50: Accessibility review
Maps | Tiles | Parks Green | Parks shown in green | App Frontend | P1 | NN-50: Not implemented
Maps | Tiles | Water Blue | Water shown in blue | App Frontend | P1 | NN-50: Not implemented
Maps | Tiles | County Borders | Show Chatham County border | App Frontend | P2 | NN-50: Not implemented
Maps | Markers | Numbered Markers | Purple circles with numbers | App Frontend | P0
Maps | Markers | Current Location | Gold marker for current POI | App Frontend | P0
Maps | Markers | Marker Popups | Info popup on click | App Frontend | P0 | NN-28: Connect to card list
Maps | Interaction | Click to Set Location | Admin map for coordinates | Admin Frontend | P0
Maps | Interaction | Auto-fit Bounds | Zoom to show all markers | App Frontend | P0
Maps | Interaction | Zoom Controls | Plus/minus buttons | App Frontend | P0
SEO | Meta Tags | Dynamic Title | Page title from POI name | App Frontend | P0
SEO | Meta Tags | Description | Meta description from teaser | App Frontend | P0
SEO | Meta Tags | Canonical URL | Canonical link tag | App Frontend | P0
SEO | Open Graph | og:title | Title for social shares | App Frontend | P0
SEO | Open Graph | og:description | Description for social | App Frontend | P0
SEO | Open Graph | og:image | Image for social preview | App Frontend | P0
SEO | Open Graph | og:type | place/event type | App Frontend | P0
SEO | Twitter | twitter:card | summary_large_image | App Frontend | P0
SEO | Twitter | twitter:title | Title for Twitter | App Frontend | P0
SEO | Twitter | twitter:description | Description for Twitter | App Frontend | P0
SEO | Structured Data | LocalBusiness JSON-LD | Schema.org LocalBusiness | App Frontend | P0
SEO | Structured Data | Event JSON-LD | Schema.org Event | App Frontend | P0 | NN-51: Implement
SEO | Structured Data | GeoCoordinates | Lat/long in structured data | App Frontend | P0
SEO | Structured Data | OpeningHours | Hours in structured data | App Frontend | P1
Sharing | Buttons | Native Share API | Device native share | App Frontend | P0
Sharing | Buttons | Facebook Share | Share to Facebook | App Frontend | P0 | NN-38: Not showing
Sharing | Buttons | Twitter Share | Share to Twitter/X | App Frontend | P0 | NN-38: Not showing
Sharing | Buttons | Email Share | Share via email | App Frontend | P0 | NN-38: Not showing
Sharing | Buttons | Copy Link | Copy URL to clipboard | App Frontend | P0
Hours | Regular | Weekly Hours | Day-by-day operating hours | Admin Backend | P0
Hours | Regular | Open/Close Times | Start and end time per day | Admin Backend | P0
Hours | Regular | Closed Days | Mark days as closed | Admin Backend | P0
Hours | Seasonal | Season Name | Label for season (Summer, Winter) | Admin Backend | P1 | NN-36: Need to add
Hours | Seasonal | Start Date | Season start date | Admin Backend | P1 | NN-36: Missing
Hours | Seasonal | End Date | Season end date | Admin Backend | P1 | NN-36: Missing
Hours | Seasonal | Seasonal Hours | Hours during season | Admin Backend | P1
Hours | Holiday | Holiday Name | Name of holiday | Admin Backend | P1
Hours | Holiday | Holiday Date | Specific date | Admin Backend | P1
Hours | Holiday | Holiday Hours | Hours or closed | Admin Backend | P1
Hours | Exceptions | Recurring Monthly | 3rd Wednesday closed, etc. | Admin Backend | P2 | NN-36: Not implemented
Hours | Exceptions | Exception Type | Closed, modified hours | Admin Backend | P2 | NN-36: Not implemented
Hours | Exceptions | Exception Override | Override regular hours | Admin Backend | P2 | NN-36: Not implemented
Hours | Frontend | Hours Display Component | HoursDisplay.jsx | App Frontend | P0
Hours | Frontend | Open Now Status | Show if currently open | App Frontend | P0
Hours | Frontend | Hours Toggle | Expand to see all hours | App Frontend | P0 | NN-36: Not working
Hours | Frontend | Date-specific Hours | Show hours for selected date | App Frontend | P0
Hours | Frontend | Override Display | Show modified/holiday indicator | App Frontend | P1 | NN-36: Not implemented
Users | CLI | Create User | manage_users.py create command | Admin Backend | P0
Users | CLI | List Users | manage_users.py list command | Admin Backend | P0
Users | CLI | Delete User | manage_users.py delete command | Admin Backend | P0
Users | CLI | Test User | manage_users.py test-user command | Admin Backend | P0
Users | CLI | Role Assignment | --role flag on create | Admin Backend | P0
Users | API | Create User Endpoint | POST /api/auth/users (Admin) | Admin Backend | P1
Users | Frontend | User Management UI | Admin page to manage users | Admin Frontend | P2 | Not implemented
Infrastructure | Docker | Dev Compose | docker-compose.yml | Infrastructure | P0
Infrastructure | Docker | Prod Compose | docker-compose.prod.yml | Infrastructure | P0
Infrastructure | Docker | Multi-stage Build | Separate build and runtime | Infrastructure | P0
Infrastructure | Docker | Health Checks | Container health monitoring | Infrastructure | P0
Infrastructure | Docker | Volume Mounts | Persistent data storage | Infrastructure | P0
Infrastructure | Database | PostgreSQL 15 | Main database server | Infrastructure | P0
Infrastructure | Database | PostGIS 3.4 | Geospatial extension | Infrastructure | P0
Infrastructure | Database | Alembic Migrations | Schema version control | Infrastructure | P0
Infrastructure | Database | Connection Pooling | SQLAlchemy pool config | Infrastructure | P0
Infrastructure | Storage | AWS S3 | Production image storage | Infrastructure | P0
Infrastructure | Storage | MinIO | Development S3 compatibility | Infrastructure | P0
Infrastructure | Storage | CloudFront CDN | Image delivery optimization | Infrastructure | P2
Infrastructure | CI/CD | GitHub Actions | Automated pipeline | Infrastructure | P0
Infrastructure | CI/CD | ECR Push | Push images to AWS ECR | Infrastructure | P0
Infrastructure | CI/CD | ECS Deploy | Deploy to AWS ECS | Infrastructure | P0
Infrastructure | Network | Docker Network | nearby-admin_default network | Infrastructure | P0
Infrastructure | Network | DNS Resolution | Container name resolution | Infrastructure | P0
Infrastructure | Network | CORS Config | Cross-origin settings | Infrastructure | P0
Database | Tables | points_of_interest | Main POI table (140+ fields) | Database | P0
Database | Tables | businesses | Business subtype table | Database | P0
Database | Tables | parks | Park subtype table | Database | P0
Database | Tables | trails | Trail subtype table | Database | P0
Database | Tables | events | Event subtype table | Database | P0
Database | Tables | categories | Category table (hierarchical) | Database | P0
Database | Tables | poi_category_association | POI-category junction | Database | P0
Database | Tables | images | Image metadata table | Database | P0
Database | Tables | attributes | Dynamic attribute definitions | Database | P0
Database | Tables | poi_relationships | POI-to-POI links | Database | P0
Database | Tables | users | Admin users table | Database | P0
Database | Tables | primary_types | POI primary types | Database | P0
Database | Tables | waitlist | Email waitlist | Database | P1
Database | Indexes | Trigram Index (name) | GIN index for fuzzy search | Database | P0
Database | Indexes | Trigram Index (city) | GIN index for city search | Database | P0
Database | Indexes | Geospatial Index | GIST index on location | Database | P0
Database | Indexes | Vector Index | IVFFlat on embedding column | Database | P0
Database | Indexes | Status Index | Index on publication_status | Database | P0
Database | Extensions | pg_trgm | Trigram text search | Database | P0
Database | Extensions | pgvector | Vector similarity search | Database | P0
Database | Extensions | PostGIS | Geospatial functions | Database | P0
Explore | Layout | Category Grid | 4 category cards with icons | App Frontend | P0
Explore | Layout | Live Counts | Show POI count per category | App Frontend | P0
Explore | Layout | Split View | List on left, map on right | App Frontend | P0
Explore | Filtering | Type Filter | Filter by POI type | App Frontend | P0
Explore | Filtering | Search Within | Search filtered results | App Frontend | P0
Explore | Filtering | Distance Sort | Sort by distance from location | App Frontend | P1
Explore | Features | Save/Favorites | Save POIs to list | App Frontend | P2 | Shows 'coming soon'
Homepage | Hero | Main Tagline | 'What's Actually Nearby' | App Frontend | P0
Homepage | Hero | Search Bar | Central search input | App Frontend | P0
Homepage | Hero | Announcement Bar | Testing location notice | App Frontend | P0
Homepage | Hero | Description | 'No Ads. No Clutter.' | App Frontend | P0
Homepage | Sections | Feature Showcase | Platform features display | App Frontend | P1
Homepage | Sections | Signup Bar | Email waitlist signup | App Frontend | P0
Homepage | Sections | Info Sections | Additional info blocks | App Frontend | P1
Homepage | Navigation | Navbar | Top navigation bar | App Frontend | P0
Homepage | Navigation | Footer | Site footer with links | App Frontend | P0
Known Issues | NN-55 | POI Update HTTP 422 | Error when updating POI | Admin Backend | P0 | Needs investigation
Known Issues | NN-4 | Can't Save New POIs | HTTP 500 on save | Admin Backend | P0 | Intermittent issue
Known Issues | NN-38 | Map Zoom Too Far | Default zoom needs adjustment | Admin Frontend | P1 | UX improvement
Known Issues | NN-38 | Address Autocomplete | Need address suggestions | Admin Frontend | P2 | Feature request
Known Issues | NN-36 | Seasonal Date Ranges | Can't specify season dates | Admin Backend | P1 | Missing feature
Known Issues | NN-36 | Recurring Exceptions | Monthly patterns not supported | Admin Backend | P2 | Missing feature
Known Issues | NN-36 | Hours Toggle Frontend | Toggle button not working | App Frontend | P0 | Bug
Known Issues | NN-46 | Venue Data Inheritance | Events don't pull from venue | Admin Backend | P1 | Missing feature
Known Issues | NN-46 | Events Page Blank | Events list showing blank | App Frontend | P0 | Bug
Known Issues | NN-50 | Map Colors A11y | Color contrast issues | App Frontend | P1 | Accessibility
Known Issues | NN-57 | Teaser Char Limit | Need 120 char limit | Admin Frontend | P0 | Missing validation
Known Issues | NN-57 | Parking Lat/Long | Missing parking coordinates | Admin Backend | P1 | Missing field
Known Issues | NN-57 | Restroom Duplicate | Can't add multiple restrooms | Admin Frontend | P1 | Missing feature
Known Issues | NN-57 | Playground Lat/Long | Missing playground coordinates | Admin Backend | P1 | Missing field
Known Issues | NN-57 | Corporate Checkboxes | Checkboxes not clickable | Admin Frontend | P0 | Bug
Known Issues | NN-48 | Verified Badge Popup | Popup not showing | App Frontend | P0 | Bug
Known Issues | NN-38 | Share Options | Only copy link showing | App Frontend | P0 | Bug
Known Issues | NN-31 | Copy Address | Only copying city | App Frontend | P0 | Bug
Known Issues | NN-28 | Map Marker Connection | Connect markers to card list | App Frontend | P1 | UX improvement