## Feature Inventory
Category | Subcategory | Feature/Component | Description | Location | Priority | Test Type | Test Method | Notes | Implementation Time | Current Status %
Authentication | Login Flow | JWT Token Generation | POST /api/auth/login returns JWT token on valid credentials | Admin Backend | P0 | AUTO | pytest: POST /api/auth/login returns valid JWT | Fully implemented with bcrypt hashing |  | 100%
Authentication | Login Flow | Login Form UI | Email/password form with validation | Admin Frontend | P0 | AUTO | Playwright: fill form, submit, verify redirect | Working with validation |  | 100%
Authentication | Login Flow | Token Storage | JWT stored in localStorage with expiration tracking | Admin Frontend | P0 | AUTO | Playwright: check localStorage after login | localStorage with expiration tracking |  | 100%
Authentication | Login Flow | Auto-redirect on Login | Redirect to dashboard after successful login | Admin Frontend | P0 | AUTO | Playwright: verify URL change after login | Redirects to dashboard |  | 100%
Authentication | Logout | Token Removal | Clear JWT from storage on logout | Admin Frontend | P0 | AUTO | Playwright: verify localStorage cleared on logout | Clears on logout |  | 100%
Authentication | Logout | Redirect to Login | Navigate to login page after logout | Admin Frontend | P0 | AUTO | Playwright: verify URL after logout | Working |  | 100%
Authentication | Session | Token Expiration Check | Validate token expiration before API calls | Admin Frontend | P0 | AUTO | pytest: mock expired token, verify rejection | Validates before API calls |  | 100%
Authentication | Session | Auto-logout on 401 | Automatically logout when API returns 401 | Admin Frontend | P0 | AUTO | Playwright: mock 401 response, verify redirect | Automatically handles |  | 100%
Authentication | Session | Get Current User | GET /api/auth/me returns current user info | Admin Backend | P0 | AUTO | pytest: GET /api/auth/me with valid token | /api/auth/me endpoint working |  | 100%
Authentication | Password | Bcrypt Hashing | Passwords hashed with bcrypt before storage | Admin Backend | P0 | AUTO | pytest: verify password hash format | Industry-standard implementation |  | 100%
Authentication | Password | Password Reset | Allow users to reset password | Admin Backend | P2 | AUTO | pytest: test reset flow when implemented | Not implemented - requires email service |  | 0%
Authorization | Roles | Admin Role | Full access to all features | Admin Backend | P0 | AUTO | pytest: verify admin can access all endpoints | Fully implemented |  | 100%
Authorization | Roles | Editor Role | Create/update POIs, manage images, no delete | Admin Backend | P0 | AUTO | pytest: verify editor permissions | DB field exists, no endpoint enforcement |  | 60%
Authorization | Roles | Viewer Role | Read-only access to all data | Admin Backend | P0 | AUTO | pytest: verify viewer is read-only | DB field exists, no endpoint enforcement |  | 60%
Authorization | Permissions | Permission Decorator | require_permission() decorator on endpoints | Admin Backend | P0 | AUTO | pytest: test decorator blocks unauthorized | Basic auth only, no RBAC enforcement |  | 25%
Authorization | Permissions | Frontend Role Check | useAuth() hook for permission checks | Admin Frontend | P0 | AUTO | Playwright: verify UI elements per role | useAuth exists, no granular checks |  | 25%
Authorization | Permissions | Protected Routes | Routes require authentication to access | Admin Frontend | P0 | AUTO | Playwright: verify redirect when not authenticated | Working |  | 100%
POI Management | Create | Create POI Endpoint | POST /api/pois/ creates new POI | Admin Backend | P0 | AUTO | pytest: POST /api/pois/ with valid data | POST /api/pois/ working |  | 100%
POI Management | Create | Create POI Form | Multi-section accordion form for POI creation | Admin Frontend | P0 | HYBRID | Playwright: fill form ¦ Manual: verify UX flow | Multi-section form implemented |  | 90%
POI Management | Create | Type Selection | Select POI type (Business, Park, Trail, Event, etc.) | Admin Frontend | P0 | AUTO | Playwright: select each type, verify form changes | 9 POI types supported |  | 100%
POI Management | Create | Auto-save | Automatically save form changes | Admin Frontend | P1 | AUTO | Playwright: type, wait, verify API call made | Implemented but may cause issues (NN-4) |  | 80%
POI Management | Read | Get POI by ID | GET /api/pois/{id} returns POI details | Admin Backend | P0 | AUTO | pytest: GET /api/pois/{id} | Working |  | 100%
POI Management | Read | Get POI by Slug | GET /api/pois/by-slug/{slug} returns POI | App Backend | P0 | AUTO | pytest: GET /api/pois/by-slug/{slug} | Working with redirects |  | 100%
POI Management | Read | List POIs (Admin) | GET /api/admin/pois/ includes drafts | Admin Backend | P0 | AUTO | pytest: verify drafts included in response | Includes drafts |  | 100%
POI Management | Read | List POIs (Public) | GET /api/pois/ only published POIs | App Backend | P0 | AUTO | pytest: verify only published returned | Filters to published only |  | 100%
POI Management | Read | POI List Table | Sortable, searchable table of all POIs | Admin Frontend | P0 | HYBRID | Playwright: sort/filter ¦ Manual: verify display | Sortable, searchable |  | 100%
POI Management | Update | Update POI Endpoint | PUT /api/pois/{id} updates POI | Admin Backend | P0 | AUTO | pytest: PUT /api/pois/{id} | NN-55: HTTP 422 errors reported |  | 70%
POI Management | Update | Update POI Form | Pre-populated form with existing data | Admin Frontend | P0 | HYBRID | Playwright: edit fields ¦ Manual: verify pre-population | Pre-populated form working |  | 90%
POI Management | Update | Partial Updates | Only send changed fields | Admin Frontend | P1 | AUTO | pytest: PATCH with subset of fields | Schema validation may be too strict |  | 70%
POI Management | Delete | Delete POI Endpoint | DELETE /api/pois/{id} removes POI | Admin Backend | P0 | AUTO | pytest: DELETE /api/pois/{id} | Working |  | 100%
POI Management | Delete | Delete Confirmation | Confirm dialog before deletion | Admin Frontend | P0 | AUTO | Playwright: verify modal appears | Dialog implemented |  | 100%
POI Management | Publication | Draft Status | POIs created as drafts by default | Admin Backend | P0 | AUTO | pytest: verify new POI has draft status | Default status working |  | 100%
POI Management | Publication | Publish POI | Change status from draft to published | Admin Backend | P0 | AUTO | pytest: verify status change endpoint | Status change working |  | 100%
POI Management | Publication | Publication Filter | Public endpoints filter by published only | App Backend | P0 | AUTO | pytest: public endpoint excludes drafts | Filters by published |  | 100%
POI Management | Publication | Status Badge | Show draft/published status in admin list | Admin Frontend | P0 | AUTO | Playwright: verify badge text matches status | Shows in admin list |  | 100%
POI Management | Slugs | Auto-generate Slug | Generate slug from name + city | Admin Backend | P0 | AUTO | pytest: create POI, verify slug format | From name + city |  | 100%
POI Management | Slugs | Unique Slug Enforcement | Append number if slug exists | Admin Backend | P0 | AUTO | pytest: create duplicate, verify suffix | Appends number if exists |  | 100%
POI Management | Slugs | SEO-friendly URLs | Use slugs in public URLs | App Frontend | P0 | AUTO | Playwright: navigate, verify URL pattern | /places/, /parks/, /trails/, /events/ |  | 100%
POI Types | Business | Business Subtype Table | Separate table for business-specific fields | Database | P0 | AUTO | pytest: verify table schema exists | 25+ fields in businesses table |  | 100%
POI Types | Business | Price Range | price_range field (e.g., $, $$, $$$) | Admin Backend | P0 | AUTO | pytest: save/retrieve price_range | $/$$/$$$/$$$ validated as Literal |  | 100%
POI Types | Business | Business Hours | Regular operating hours | Admin Backend | P0 | AUTO | Playwright: verify hours section | Shows hours but toggle broken (NN-36) |  | 80%
POI Types | Business | Business Amenities | WiFi, parking, restrooms, etc. | Admin Backend | P0 | AUTO | pytest: verify amenities fields | business_amenities, entertainment_options, youth_amenities JSONB |  | 100%
POI Types | Business | Business Detail Page | BusinessDetail.jsx component | App Frontend | P0 | HYBRID | Playwright: sections exist ¦ Manual: design review | BusinessDetail.jsx comprehensive - price, hours, WiFi, menu, restrooms |  | 100%
POI Types | Business | Key Facilities Display | Show restrooms, wheelchair, WiFi, pet-friendly | App Frontend | P0 | AUTO | Playwright: verify icons render | Icons working for restrooms, wheelchair, WiFi, pet-friendly |  | 85%
POI Types | Park | Park Subtype Table | Separate table for park-specific fields | Database | P0 | AUTO | pytest: verify table exists | 18+ fields in parks table |  | 100%
POI Types | Park | Drone Policy | drones_allowed field | Admin Backend | P1 | AUTO | pytest: save/retrieve drone policy | drone_usage_policy field in Park subtype |  | 100%
POI Types | Park | Park Facilities | Playgrounds, pavilions, trails | Admin Backend | P0 | AUTO | pytest: verify facilities JSONB | Implemented via facilities JSONB |  | 100%
POI Types | Park | Natural Features | Lakes, forests, fields | Admin Backend | P1 | AUTO | pytest: verify array field | natural_features JSONB array working |  | 100%
POI Types | Park | Park Detail Page | ParkDetail.jsx component | App Frontend | P0 | HYBRID | Playwright: sections ¦ Manual: design | ParkDetail.jsx - hours, parking, playground. Missing hunting/fishing display |  | 80%
POI Types | Park | Playground Info | Playground type, surface, notes | Admin Backend | P0 | AUTO | pytest: verify playground fields | playground_available, types, surface_types. NN-57: Missing lat/long |  | 75%
POI Types | Park | Playground Duplicates | Add multiple playgrounds per park | Admin Backend | P1 | AUTO | Playwright: click add, verify section | NN-57: No duplicate button implemented |  | 0%
POI Types | Trail | Trail Subtype Table | Separate table for trail-specific fields | Database | P0 | AUTO | pytest: verify table exists | 20+ fields in trails table |  | 100%
POI Types | Trail | Trail Length | length_miles field | Admin Backend | P0 | AUTO | pytest: save/retrieve length | length_text with multi-segment support |  | 100%
POI Types | Trail | Trail Difficulty | Easy, Moderate, Hard | Admin Backend | P0 | AUTO | pytest: verify difficulty enum | difficulty with auto-populated difficulty_description |  | 100%
POI Types | Trail | Route Type | Loop, out-and-back, point-to-point | Admin Backend | P0 | AUTO | pytest: verify route_type values | Loop, out-and-back, point-to-point supported |  | 100%
POI Types | Trail | Surface Types | Dirt, gravel, asphalt, etc. | Admin Backend | P0 | AUTO | Playwright: verify surfaces | Trail surfaces displayed |  | 100%
POI Types | Trail | Trailhead Coordinates | Lat/long for trail start | Admin Backend | P0 | AUTO | pytest: verify lat/long fields | trailhead_latitude/longitude fields |  | 100%
POI Types | Trail | Trail Exit Coordinates | Lat/long for trail end | Admin Backend | P0 | AUTO | pytest: verify lat/long fields | trail_exit_latitude/longitude fields |  | 100%
POI Types | Trail | Trailhead Photos | Upload photos of trailhead | Admin Backend | P0 | AUTO | pytest: upload, verify type | NN-57: Need 10 images, currently limited to 1 |  | 50%
POI Types | Trail | Trail Exit Photos | Upload photos of trail exit | Admin Backend | P0 | AUTO | pytest: upload trail_exit | 1 max (need 10 per NN-57) |  | 100%
POI Types | Trail | Trail Detail Page | TrailDetail.jsx component | App Frontend | P0 | HYBRID | Playwright: elements ¦ Manual: layout | TrailDetail.jsx excellent - length, difficulty, surfaces, address |  | 90%
POI Types | Trail | Downloadable Maps | PDF map uploads | Admin Backend | P1 | AUTO | pytest: upload PDF | 5 max, 50MB each, PDF support |  | 100%
POI Types | Event | Event Subtype Table | Separate table for event-specific fields | Database | P0 | AUTO | pytest: verify table exists | 22+ fields in events table |  | 100%
POI Types | Event | Start DateTime | Event start date and time | Admin Backend | P0 | AUTO | pytest: verify timestamp saves | start_datetime TIMESTAMP field |  | 100%
POI Types | Event | End DateTime | Event end date and time | Admin Backend | P0 | AUTO | pytest: verify timestamp saves | end_datetime TIMESTAMP field |  | 100%
POI Types | Event | Repeat Pattern | Recurring event pattern (weekly, monthly) | Admin Backend | P1 | AUTO | pytest: verify JSONB pattern | is_repeating boolean + repeat_pattern JSONB |  | 100%
POI Types | Event | Organizer Info | Name, email, phone of organizer | Admin Backend | P0 | AUTO | Playwright: verify organizer | Organizer name displayed |  | 100%
POI Types | Event | Venue Selection | Link event to venue POI | Admin Backend | P0 | AUTO | Playwright: select venue | VenueSelector component exists but incomplete |  | 80%
POI Types | Event | Venue Data Inheritance | Pull address, parking, etc. from venue | Admin Backend | P1 | AUTO | pytest: verify venue data | NOT IMPLEMENTED |  | 0%
POI Types | Event | Ticket URL | Link to buy tickets | Admin Backend | P0 | AUTO | pytest: verify URL saves | ticket_url field working |  | 100%
POI Types | Event | Is Free | Boolean flag for free events | Admin Backend | P0 | AUTO | pytest: verify boolean | is_free boolean field |  | 100%
POI Types | Event | Vendor Management | List of vendors at event | Admin Backend | P1 | AUTO | pytest: add vendors | has_vendors, vendor_types, vendor_fee fields exist. Display incomplete |  | 80%
POI Types | Event | Event Detail Page | EventDetail.jsx component | App Frontend | P0 | HYBRID | Playwright: sections ¦ Manual: design | EventDetail.jsx functional but missing vendor info, venue settings, repeat pattern display |  | 70%
POI Types | Event | Past Event Exclusion | Hide events after end date in Nearby | App Backend | P0 | AUTO | pytest: create past event, verify filtered | Automatically filters past events in Nearby |  | 100%
POI Types | Event | Events Page | List of all events | App Frontend | P0 | AUTO | Playwright: navigate, verify renders | NN-57: Blank white screen - form doesn't render |  | 0%
POI Types | Services | Services POI Type | Service provider listings | Admin Backend | P2 | AUTO | pytest: create service POI | Enum defined, no subtype table, no form, uses GenericDetail |  | 15%
POI Types | Youth Activities | Youth Activities POI Type | Youth programs and activities | Admin Backend | P2 | AUTO | pytest: create youth POI | Enum + youth_amenities field, no dedicated form/detail |  | 25%
POI Types | Jobs | Jobs POI Type | Job listings | Admin Backend | P3 | AUTO | pytest: create job POI | Enum only - no model, form, or detail page |  | 5%
POI Types | Volunteer | Volunteer Opportunities Type | Volunteer positions | Admin Backend | P3 | AUTO | pytest: create volunteer POI | Enum only - no infrastructure |  | 5%
POI Types | Disaster Hubs | Disaster Hubs POI Type | Emergency resources | Admin Backend | P2 | AUTO | pytest: create disaster POI | is_disaster_hub, emergency_protocols fields. No dedicated detail page |  | 35%
POI Form | Core Information | Name Field | POI name input | Admin Frontend | P0 | AUTO | Playwright: type, verify saves | Working |  | 100%
POI Form | Core Information | Type Selection | POI type dropdown | Admin Frontend | P0 | AUTO | Playwright: select each type, verify form changes | 9 POI types supported |  | 100%
POI Form | Core Information | Teaser Paragraph | Short description (120 chars) | Admin Frontend | P0 | AUTO | Playwright: verify char limit | NN-57: Need 120 char limit with live counter |  | 80%
POI Form | Core Information | Primary Type | Primary business type selection | Admin Frontend | P0 | AUTO | Playwright: select, verify | Selection working |  | 100%
POI Form | Core Information | Listing Type | Free, Paid, Sponsor, etc. | Admin Frontend | P0 | AUTO | Playwright: select each option | Free/Paid/Paid Founding/Sponsor/Community Comped |  | 100%
POI Form | Core Information | Lat/Long Accuracy Flag | Mark if coordinates are most accurate | Admin Frontend | P1 | AUTO | Playwright: click, verify state | NN-57: Need 'most accurate' button |  | 0%
POI Form | Location | Street Address | Street address input | Admin Frontend | P0 | AUTO | Playwright: type address | Working |  | 100%
POI Form | Location | City | City input | Admin Frontend | P0 | AUTO | Playwright: type/select city | NN-38: Should be dropdown for Chatham County cities |  | 80%
POI Form | Location | State | State input | Admin Frontend | P0 | AUTO | Playwright: verify default | NN-38: Should default to NC |  | 80%
POI Form | Location | Zip Code | Zip code input | Admin Frontend | P0 | AUTO | Playwright: type, verify format | Working |  | 100%
POI Form | Location | County | County input | Admin Frontend | P0 | AUTO | Playwright: verify default | NN-38: Should default to Chatham |  | 80%
POI Form | Location | Coordinates Picker | Map click to set lat/long | Admin Frontend | P0 | AUTO | Playwright: click map, verify coords | Map click to set lat/long working |  | 100%
POI Form | Location | Map Zoom Level | Adjust default zoom for easier use | Admin Frontend | P1 | MANUAL | Manual: verify zoom is usable | NN-38: Improved but still needs tuning |  | 70%
POI Form | Location | Address Autocomplete | Suggest addresses as user types | Admin Frontend | P2 | AUTO | Playwright: type, verify suggestions | NOT IMPLEMENTED |  | 0%
POI Form | Location | Front Door Coordinates | Separate lat/long for entrance | Admin Frontend | P0 | AUTO | Playwright: verify fields update | Separate lat/long fields working |  | 100%
POI Form | Parking | Parking Types | Multi-select parking options | Admin Frontend | P0 | AUTO | Playwright: select multiple | Multi-select checkboxes working |  | 100%
POI Form | Parking | Parking Notes | Text field for parking details | Admin Frontend | P0 | AUTO | Playwright: type, verify saves | NN-57: Missing on free listings |  | 70%
POI Form | Parking | Parking Lat/Long | Coordinates for parking lot | Admin Frontend | P0 | AUTO | pytest: verify fields | MISSING field |  | 0%
POI Form | Parking | Parking Photos | Upload parking area photos | Admin Frontend | P0 | AUTO | pytest: upload parking photo | 5 max, parking type |  | 100%
POI Form | Parking | Additional Parking | Add multiple parking locations | Admin Frontend | P1 | AUTO | Playwright: click add | NN-57: Goes to white screen when clicked |  | 0%
POI Form | Parking | Public Transit Info | Transit access details | Admin Frontend | P1 | AUTO | Playwright: type, verify | NN-57: Missing on free listings |  | 70%
POI Form | Parking | Expect to Pay | Parking fee indicator | Admin Frontend | P0 | AUTO | Playwright: select option | NN-57: Missing on free listings |  | 70%
POI Form | Contact | Phone Number | Primary phone input | Admin Frontend | P0 | AUTO | Playwright: type, verify format | Working |  | 100%
POI Form | Contact | Email | Contact email input | Admin Frontend | P0 | AUTO | Playwright: type, verify validation | Working with validation |  | 100%
POI Form | Contact | Website | Website URL input | Admin Frontend | P0 | AUTO | Playwright: type URL | URL input working |  | 100%
POI Form | Social Media | Instagram | Instagram handle/URL | Admin Frontend | P0 | AUTO | Playwright: type handle | Working |  | 100%
POI Form | Social Media | Facebook | Facebook page URL | Admin Frontend | P0 | AUTO | Playwright: type URL | Working |  | 100%
POI Form | Social Media | X/Twitter | Twitter/X handle | Admin Frontend | P0 | AUTO | Playwright: type handle | Working |  | 100%
POI Form | Social Media | TikTok | TikTok handle | Admin Frontend | P1 | AUTO | Playwright: type handle | Working |  | 100%
POI Form | Social Media | LinkedIn | LinkedIn page URL | Admin Frontend | P1 | AUTO | Playwright: type URL | Working |  | 100%
POI Form | Categories | Main Category Selector | Select primary category (required) | Admin Frontend | P0 | AUTO | Playwright: select, verify | TreeCategorySelector with hierarchy |  | 100%
POI Form | Categories | Secondary Categories | Select additional categories | Admin Frontend | P0 | AUTO | Playwright: multi-select | Multi-select working |  | 100%
POI Form | Categories | Category Tree Display | Hierarchical category picker | Admin Frontend | P0 | HYBRID | Playwright: expand ¦ Manual: hierarchy | Hierarchical picker with expand/collapse |  | 100%
POI Form | Categories | Type-filtered Categories | Only show categories for POI type | Admin Frontend | P0 | AUTO | Playwright: change type, verify filter | Filters by POI type via applicable_to |  | 100%
POI Form | Categories | Business Category Limit | Limit to 1 category for free business | Admin Frontend | P0 | AUTO | Playwright: try >1, verify blocked | NN-57: Free business allows multiple (should be 1) |  | 50%
POI Form | Hours | Regular Hours Input | Day-by-day hours picker | Admin Frontend | P0 | AUTO | Playwright: set hours each day | Day-by-day picker with multiple periods |  | 100%
POI Form | Hours | Seasonal Hours | Hours for specific seasons | Admin Frontend | P1 | AUTO | pytest: save, verify | Backend complete, frontend partial |  | 90%
POI Form | Hours | Holiday Hours | Special holiday hours | Admin Frontend | P1 | AUTO | pytest: save, verify | Open/closed/modified statuses |  | 95%
POI Form | Hours | Recurring Exceptions | Monthly exceptions (3rd Wed closed) | Admin Frontend | P2 | AUTO | pytest: verify patterns | IMPLEMENTED - 3rd Wednesday patterns work |  | 100%
POI Form | Facilities | Public Restrooms Toggle | Are restrooms available? | Admin Frontend | P0 | AUTO | Playwright: toggle, verify | Working |  | 100%
POI Form | Facilities | Restroom Options | Restroom type checkboxes | Admin Frontend | P0 | AUTO | Playwright: select options | Checkboxes working |  | 100%
POI Form | Facilities | Restroom Description | Text field for restroom details | Admin Frontend | P0 | AUTO | Playwright: type, verify | NN-57: Missing field |  | 0%
POI Form | Facilities | Restroom Lat/Long | Coordinates for restroom location | Admin Frontend | P0 | AUTO | Playwright: enter coords | NN-57: Missing field |  | 0%
POI Form | Facilities | Restroom Photos | Upload restroom photos | Admin Frontend | P0 | AUTO | pytest: upload restroom photo | 10 max, restroom type |  | 100%
POI Form | Facilities | Add Another Restroom | Duplicate restroom section | Admin Frontend | P1 | AUTO | Playwright: click add | Parks only - need for Trails/Events |  | 50%
POI Form | Facilities | Wheelchair Accessible | Yes/No/Unknown selector | Admin Frontend | P0 | AUTO | Playwright: select | Working |  | 100%
POI Form | Facilities | Accessibility Details | Text field for details | Admin Frontend | P0 | AUTO | Playwright: type | Text field working |  | 100%
POI Form | Facilities | WiFi Available | Free WiFi checkbox | Admin Frontend | P0 | AUTO | Playwright: toggle | Working |  | 100%
POI Form | Facilities | Pet Policy | Pet-friendly options | Admin Frontend | P0 | AUTO | Playwright: select options | Working with options |  | 100%
POI Form | Facilities | Alcohol Available | Yes/No selector | Admin Frontend | P0 | AUTO | Playwright: select | Working |  | 100%
POI Form | Facilities | Alcohol Policy Details | Text for alcohol policy | Admin Frontend | P0 | AUTO | Playwright: type | NN-57: Missing description paragraph |  | 0%
POI Form | Outdoor Features | Drone Usage Policy | Drone rules text field | Admin Frontend | P1 | AUTO | Playwright: type policy | Working for events/parks/trails |  | 100%
POI Form | Outdoor Features | Fishing Info | Fishing availability and details | Admin Frontend | P1 | AUTO | Playwright: select options | fishing_allowed, fishing_types working |  | 100%
POI Form | Outdoor Features | Hunting Info | Hunting availability and details | Admin Frontend | P1 | AUTO | Playwright: select options | hunting_allowed, hunting_types working |  | 100%
POI Form | Rentals | Rentals Available | Toggle for rental availability | Admin Frontend | P1 | AUTO | Playwright: toggle | Toggle with conditional fields |  | 100%
POI Form | Rentals | Rental Description | Text field for rental details | Admin Frontend | P1 | AUTO | Playwright: type | Rich text working |  | 100%
POI Form | Rentals | Rental Link | URL for booking | Admin Frontend | P1 | AUTO | Playwright: type URL | URL field working |  | 100%
POI Form | Rentals | Rental Photos | Upload rental item photos | Admin Frontend | P1 | AUTO | pytest: upload rental photo | 10 max, rental type |  | 100%
POI Form | Rentals | Rental Pricing Box | Pricing input section | Admin Frontend | P3 | AUTO | Playwright: verify removed | NN-57: Remove - not used |  | 100%
POI Form | Community | Community Connections | Links to related content | Admin Frontend | P1 | AUTO | Playwright: add links | Links working |  | 80%
POI Form | Community | Article Links | Links with custom titles | Admin Frontend | P1 | AUTO | Playwright: add with title | NN-57: Need custom title field for DoorDash, Calendly |  | 70%
POI Form | Community | Community Impact | Community involvement section | Admin Frontend | P2 | AUTO | Playwright: type | NN-57: Remove from free listings |  | 80%
POI Form | Corporate | Comments Restrictions | Restrictions on public comments | Admin Frontend | P2 | AUTO | Playwright: click radio | NN-57: Checkbox not clickable - Radio.Group styling issue |  | 0%
POI Form | Corporate | Social Media Restrictions | Platforms that can't be used | Admin Frontend | P2 | AUTO | Playwright: click checkboxes | NN-57: Checkbox not clickable |  | 0%
POI Form | Corporate | Pre-approval Required | Approval before featuring | Admin Frontend | P2 | AUTO | Playwright: click radio | NN-57: Checkbox not clickable |  | 0%
POI Form | Corporate | Branding Requirements | Required/avoided language | Admin Frontend | P2 | AUTO | Playwright: click radio | NN-57: Checkbox not clickable |  | 0%
POI Form | Misc | Long Description | Rich text editor for full description | Admin Frontend | P0 | AUTO | Playwright: type rich text | Rich text editor working |  | 100%
POI Form | Misc | Internal Notes | Admin-only notes | Admin Frontend | P1 | AUTO | Playwright: type notes | Working |  | 100%
POI Form | Misc | History Paragraph | Historical information | Admin Frontend | P2 | AUTO | Playwright: type history | Working for paid listings |  | 100%
POI Form | Misc | Verified Flag | Mark as verified by team | Admin Frontend | P0 | AUTO | Playwright: toggle | Working |  | 100%
POI Form | Misc | Disaster Hub Flag | Mark as disaster resource | Admin Frontend | P2 | AUTO | Playwright: toggle | Working |  | 100%
Categories | Structure | Hierarchical Tree | Categories with parent-child relationships | Database | P0 | AUTO | pytest: create nested, verify structure | Unlimited nesting with self-referencing parent_id |  | 100%
Categories | Structure | Unlimited Nesting | Any depth of category nesting | Admin Backend | P0 | AUTO | pytest: create 5+ levels | No depth limit, proper tree building |  | 100%
Categories | Structure | POI Type Filtering | applicable_types array per category | Admin Backend | P0 | AUTO | pytest: filter by type | applicable_to ARRAY with .contains() query |  | 100%
Categories | Structure | Slug Generation | Auto-generate category slugs | Admin Backend | P0 | AUTO | pytest: create, verify slug | Auto-generated from name |  | 100%
Categories | API | Get Category Tree | GET /api/categories/tree endpoint | Admin Backend | P0 | AUTO | pytest: GET /api/categories/tree | GET /api/categories/tree returns nested structure |  | 100%
Categories | API | Get by POI Type | GET /api/categories/by-poi-type/{type} | Admin Backend | P0 | AUTO | pytest: GET by-poi-type endpoint | GET /api/categories/by-poi-type/{type} working |  | 100%
Categories | API | Create Category | POST /api/categories/ endpoint | Admin Backend | P0 | AUTO | pytest: POST /api/categories/ | POST /api/categories/ with validation |  | 100%
Categories | API | Update Category | PUT /api/categories/{id} endpoint | Admin Backend | P0 | AUTO | pytest: PUT endpoint | PUT /api/categories/{id} working |  | 100%
Categories | API | Delete Category | DELETE /api/categories/{id} endpoint | Admin Backend | P0 | AUTO | pytest: DELETE, verify children blocked | Blocks if children exist (no reparenting) |  | 100%
Categories | API | Circular Reference Prevention | Prevent category from being its own parent | Admin Backend | P0 | AUTO | pytest: try self-parent, verify error | NOT IMPLEMENTED - major gap. No is_descendant() check |  | 20%
Categories | Frontend | Category List Page | Admin page showing all categories | Admin Frontend | P0 | AUTO | Playwright: navigate, verify table | Admin page with hierarchical display |  | 100%
Categories | Frontend | Category Selector | Hierarchical picker in POI form | Admin Frontend | P0 | HYBRID | Playwright: expand ¦ Manual: usability | TreeCategorySelector with expand/collapse |  | 100%
Categories | Frontend | Main Category Badge | Indicate main vs secondary | Admin Frontend | P0 | AUTO | Playwright: verify badge | is_main flag in poi_category_association |  | 100%
Images | Storage | S3 Storage | Store images in AWS S3 | Admin Backend | P0 | AUTO | pytest: upload, verify S3 URL | boto3 integration with CloudFront support |  | 100%
Images | Storage | MinIO (Dev) | S3-compatible local storage | Infrastructure | P0 | AUTO | pytest: upload to MinIO | S3-compatible with auto-bucket creation |  | 100%
Images | Storage | Database Storage Deprecated | No longer store binary in DB | Admin Backend | P0 | AUTO | pytest: verify no binary in DB | S3-only storage now |  | 100%
Images | Types | Main Image | Primary featured image | Admin Backend | P0 | AUTO | pytest: upload, verify limit=1 | 1 max, main type |  | 100%
Images | Types | Gallery Images | Additional photo gallery | Admin Backend | P0 | AUTO | pytest: upload 20, verify limit | 20 max, gallery type |  | 100%
Images | Types | Entry Photos | Entrance/storefront photos | Admin Backend | P0 | AUTO | pytest: upload entry photo | 3 max, entry type |  | 100%
Images | Types | Parking Photos | Parking area photos | Admin Backend | P0 | AUTO | pytest: upload parking photo | 5 max, parking type |  | 100%
Images | Types | Restroom Photos | Restroom photos | Admin Backend | P0 | AUTO | pytest: upload restroom photo | 10 max, restroom type |  | 100%
Images | Types | Rental Photos | Rental equipment photos | Admin Backend | P1 | AUTO | pytest: upload rental photo | 10 max, rental type |  | 100%
Images | Types | Playground Photos | Playground photos | Admin Backend | P1 | AUTO | pytest: upload playground photo | 10 max, playground type |  | 100%
Images | Types | Menu Photos | Menu images | Admin Backend | P0 | AUTO | pytest: upload menu photo | 10 max, menu type |  | 100%
Images | Types | Trail Head Photos | Trailhead location photos | Admin Backend | P0 | AUTO | pytest: upload trail_head | 1 max (need 10 per NN-57) |  | 100%
Images | Types | Trail Exit Photos | Trail exit location photos | Admin Backend | P0 | AUTO | pytest: upload trail_exit | 1 max (need 10 per NN-57) |  | 100%
Images | Types | Map Images | Map graphics | Admin Backend | P1 | AUTO | pytest: upload map image | 5 max, map type |  | 100%
Images | Types | Downloadable Maps | PDF maps (20MB max) | Admin Backend | P1 | AUTO | pytest: upload PDF | 5 max, 50MB each, PDF support |  | 100%
Images | Variants | Original Size | Full resolution upload | Admin Backend | P0 | AUTO | pytest: verify dimensions | Preserved on upload |  | 100%
Images | Variants | XLarge (1920x1080) | Hero image size | Admin Backend | P0 | AUTO | pytest: verify variant | Auto-generated via PIL |  | 100%
Images | Variants | Large (1200x800) | Detail page size | Admin Backend | P0 | AUTO | pytest: verify variant | Auto-generated |  | 100%
Images | Variants | Medium (600x400) | Card/list size | Admin Backend | P0 | AUTO | pytest: verify variant | Auto-generated |  | 100%
Images | Variants | Thumbnail (200x200) | Grid preview size | Admin Backend | P0 | AUTO | pytest: verify thumbnail | Auto-generated |  | 100%
Images | Variants | Auto-generation | Create variants on upload | Admin Backend | P0 | AUTO | pytest: upload, verify all variants | PIL LANCZOS resampling, per-type variants |  | 100%
Images | Upload | Single Upload | POST /api/images/upload/{poi_id} | Admin Backend | P0 | AUTO | pytest: POST single file | POST /api/images/upload/{poi_id} |  | 100%
Images | Upload | Bulk Upload | POST /api/images/bulk-upload/{poi_id} | Admin Backend | P0 | AUTO | pytest: POST multiple files | POST /api/images/upload-multiple/{poi_id} |  | 100%
Images | Upload | Drag-and-Drop | Drag files to upload | Admin Frontend | P0 | AUTO | Playwright: simulate drop | Mantine Dropzone with progress tracking |  | 100%
Images | Upload | File Size Limit | 10MB max (20MB for PDFs) | Admin Backend | P0 | AUTO | pytest: upload >10MB, verify rejection | Per-type limits (5MB-50MB) |  | 100%
Images | Upload | Format Validation | JPEG, PNG, WebP, PDF only | Admin Backend | P0 | AUTO | pytest: upload .exe, verify rejection | MIME type checking for JPEG, PNG, WebP, PDF |  | 100%
Images | Management | Reorder Images | Drag to reorder gallery | Admin Frontend | P0 | AUTO | Playwright: drag reorder | @hello-pangea/dnd drag reordering |  | 100%
Images | Management | Alt Text | Add alt text for accessibility | Admin Frontend | P0 | AUTO | Playwright: edit, verify saves | Inline editing with debounced save |  | 100%
Images | Management | Captions | Add captions to images | Admin Frontend | P1 | AUTO | Playwright: edit, verify saves | Inline editing with debounced save |  | 100%
Images | Management | Delete Image | Remove image from POI | Admin Frontend | P0 | AUTO | Playwright: delete, verify S3 cleanup | S3 cleanup on deletion |  | 100%
Attributes | Types | Text Attribute | Single line text input | Admin Backend | P0 | AUTO | pytest: create text attribute | Only categories implemented, not field input types |  | 15%
Attributes | Types | Textarea Attribute | Multi-line text input | Admin Backend | P0 | AUTO | pytest: create textarea | Categories only, not field types |  | 15%
Attributes | Types | Number Attribute | Numeric input with min/max | Admin Backend | P0 | AUTO | pytest: create number with min/max | Categories only |  | 15%
Attributes | Types | Select Attribute | Single choice dropdown | Admin Backend | P0 | AUTO | pytest: create select | Categories only |  | 15%
Attributes | Types | Multi-select Attribute | Multiple choice checkboxes | Admin Backend | P0 | AUTO | pytest: create multi-select | Categories only |  | 15%
Attributes | Types | Checkbox Attribute | Boolean toggle | Admin Backend | P0 | AUTO | pytest: create checkbox | Categories only |  | 15%
Attributes | Types | Date Attribute | Date picker input | Admin Backend | P0 | AUTO | pytest: create date | Categories only |  | 15%
Attributes | Types | Time Attribute | Time picker input | Admin Backend | P0 | AUTO | pytest: create time | Categories only |  | 15%
Attributes | Types | URL Attribute | URL input with validation | Admin Backend | P0 | AUTO | pytest: create URL | Categories only |  | 15%
Attributes | Types | Email Attribute | Email input with validation | Admin Backend | P0 | AUTO | pytest: create email | Categories only |  | 15%
Attributes | Config | POI Type Filtering | Limit attributes to POI types | Admin Backend | P0 | AUTO | pytest: filter by type | applicable_to ARRAY with .contains() query |  | 100%
Attributes | Config | Required Flag | Mark attribute as required | Admin Backend | P0 | AUTO | pytest: mark required, verify validation | Not in database model |  | 0%
Attributes | Config | Default Value | Set default value | Admin Backend | P1 | AUTO | pytest: set default, verify applied | Not implemented |  | 0%
Attributes | Config | Help Text | Display help text to users | Admin Backend | P1 | AUTO | Playwright: verify help displays | Not implemented |  | 0%
Attributes | Config | Display Order | Control attribute order | Admin Backend | P1 | AUTO | pytest: set order, verify sorting | sort_order field working |  | 100%
Attributes | Frontend | Dynamic Form Rendering | Render attributes based on config | Admin Frontend | P0 | HYBRID | Playwright: fields ¦ Manual: correct type | DynamicAttributeForm renders checkboxes only |  | 50%
Attributes | Frontend | Validation | Client-side validation per type | Admin Frontend | P0 | AUTO | pytest: submit invalid, verify error | Basic presence only, no type-specific validation |  | 30%
Relationships | Types | Event-Venue | Link event to venue location | Admin Backend | P0 | AUTO | pytest: create event-venue | venue relationship type fully implemented |  | 100%
Relationships | Types | Event-Vendor | Link event to vendor businesses | Admin Backend | P1 | AUTO | pytest: create event-vendor | vendor relationship type working |  | 100%
Relationships | Types | Event-Sponsor | Link event to sponsors | Admin Backend | P2 | AUTO | pytest: create event-sponsor | sponsor relationship type working |  | 100%
Relationships | Types | Trail-in-Park | Link trail to containing park | Admin Backend | P0 | AUTO | pytest: create trail-in-park | trail_in_park type with strict validation |  | 100%
Relationships | Types | Service Provider | Link service to POI | Admin Backend | P2 | AUTO | pytest: create service provider | service_provider bidirectional working |  | 100%
Relationships | Types | Related POIs | Generic relation between POIs | Admin Backend | P1 | AUTO | pytest: create related link | related type for generic connections |  | 100%
Relationships | API | Create Relationship | POST /api/relationships/ | Admin Backend | P0 | AUTO | pytest: POST /api/relationships/ | POST /api/relationships/ with validation |  | 100%
Relationships | API | Get POI Relationships | GET /api/relationships/{poi_id} | Admin Backend | P0 | AUTO | pytest: GET endpoint | Returns both outgoing and incoming |  | 100%
Relationships | API | Delete Relationship | DELETE /api/relationships/... | Admin Backend | P0 | AUTO | pytest: DELETE | DELETE endpoint working |  | 100%
Relationships | Frontend | Relationship Manager | UI to add/remove relationships | Admin Frontend | P0 | AUTO | Playwright: open modal, add | UI modal for add/remove with color-coded badges |  | 100%
Relationships | Frontend | POI Search for Linking | Search POIs to create link | Admin Frontend | P0 | AUTO | Playwright: search, select | RelationshipSearch component working |  | 100%
Relationships | Frontend | Display Relationships | Show linked POIs on detail page | App Frontend | P1 | AUTO | Playwright: verify on detail page | NN-40: NOT shown on public detail pages |  | 0%
Search | Keyword | pg_trgm Fuzzy Search | Trigram-based fuzzy matching | App Backend | P0 | AUTO | pytest: 'coffe' finds 'coffee' | Extension working, 'coffe' finds 'coffee' |  | 100%
Search | Keyword | Search Endpoint | GET /api/pois/search?q=... | App Backend | P0 | AUTO | pytest: GET /api/pois/search | GET /api/pois/search?q=... |  | 100%
Search | Keyword | Similarity Threshold | 0.3 minimum similarity | App Backend | P0 | AUTO | pytest: test threshold | 0.3 minimum similarity configured |  | 100%
Search | Keyword | Name Weighting | Name matches weighted 2x | App Backend | P0 | AUTO | pytest: verify name ranks higher | Name matches weighted 2x |  | 100%
Search | Semantic | Embedding Model | michaelfeil/embeddinggemma-300m (~1GB) | App Backend | P0 | AUTO | pytest: verify model loads | michaelfeil/embeddinggemma-300m ~1GB, loads on startup |  | 90%
Search | Semantic | Vector Storage | pgvector extension for embeddings | Database | P0 | AUTO | pytest: verify column exists (prod) | pgvector on prod, NOT on local dev |  | 65%
Search | Semantic | Semantic Endpoint | GET /api/pois/semantic-search?q=... | App Backend | P0 | AUTO | pytest: GET semantic-search | GET /api/pois/semantic-search, falls back to keyword |  | 90%
Search | Semantic | Natural Language | Understand queries like 'dog friendly cafe' | App Backend | P0 | HYBRID | pytest: query ¦ Manual: relevance | Understands 'dog friendly cafe' intent |  | 90%
Search | Semantic | Fallback to Keyword | Use keyword if embeddings unavailable | App Backend | P0 | AUTO | pytest: disable vector, verify fallback | Graceful degradation when embeddings unavailable |  | 100%
Search | Hybrid | Combined Search | 30% keyword + 70% semantic | App Backend | P0 | AUTO | pytest: verify hybrid scoring | 30% keyword + 70% semantic working |  | 100%
Search | Hybrid | Configurable Weights | Adjust keyword/semantic balance | App Backend | P1 | AUTO | pytest: change weights | Hardcoded but functioning |  | 80%
Search | Hybrid | Hybrid Endpoint | GET /api/pois/hybrid-search?q=... | App Backend | P0 | AUTO | pytest: GET hybrid-search | GET /api/pois/hybrid-search working |  | 100%
Search | Frontend | Search Bar Component | SearchBar.jsx with input | App Frontend | P0 | AUTO | Playwright: type, verify dropdown | SearchBar.jsx with full functionality |  | 100%
Search | Frontend | Debounced Input | 300ms delay before API call | App Frontend | P0 | AUTO | Playwright: type fast, verify single call | 300ms delay before API call |  | 100%
Search | Frontend | Search Dropdown | Results list with keyboard nav | App Frontend | P0 | AUTO | Playwright: verify results | Results list with keyboard navigation |  | 100%
Search | Frontend | Keyboard Navigation | Arrow keys, Enter, Escape | App Frontend | P0 | AUTO | Playwright: arrow, enter | Arrow keys, Enter, Escape all working |  | 100%
Search | Frontend | Result Highlighting | Highlight selected result | App Frontend | P0 | AUTO | Playwright: arrow, verify highlight | Selected result highlighted |  | 100%
Nearby | Core | Nearby API Endpoint | GET /api/pois/{poi_id}/nearby | App Backend | P0 | AUTO | pytest: GET /api/pois/{id}/nearby | GET /api/pois/{id}/nearby?radius_miles= |  | 100%
Nearby | Core | Distance Calculation | PostGIS ST_DWithin/ST_Distance | App Backend | P0 | AUTO | pytest: verify distance accuracy | PostGIS ST_DWithin/ST_Distance in meters |  | 100%
Nearby | Core | Miles to Meters | Convert miles to meters for PostGIS | App Backend | P0 | AUTO | pytest: verify conversion | Conversion working (1609.34m/mile) |  | 100%
Nearby | Core | Sort by Distance | Return nearest first | App Backend | P0 | AUTO | pytest: verify ascending order | Returns nearest first |  | 100%
Nearby | Filters | Radius Dropdown | 1, 3, 5, 10, 15 miles | App Frontend | P0 | AUTO | Playwright: select, verify results | 1, 3, 5, 10, 15 miles options |  | 100%
Nearby | Filters | Type Filter Pills | All, Businesses, Events, Parks, Trails | App Frontend | P0 | AUTO | Playwright: click, verify filter | All, Businesses, Events, Parks, Trails with icons |  | 100%
Nearby | Filters | Youth Events Filter | Filter for youth activities | App Frontend | P1 | AUTO | Playwright: click Youth | Filters by category names containing youth/kids/family |  | 100%
Nearby | Filters | Date Presets | Today, Tomorrow, This Weekend | App Frontend | P0 | AUTO | Playwright: select Today | Today, Tomorrow, This Weekend working |  | 100%
Nearby | Filters | Custom Date Picker | Select specific date | App Frontend | P0 | AUTO | Playwright: pick date | Calendar picker, no manual entry |  | 100%
Nearby | Filters | Search Within Nearby | Hybrid search filtered to nearby | App Frontend | P0 | AUTO | Playwright: search, verify filtered | Hybrid search filtered to nearby POI IDs |  | 100%
Nearby | Filters | Clear Filters Button | Reset all filters | App Frontend | P0 | AUTO | Playwright: click, verify reset | Reset all filters working |  | 100%
Nearby | Map | Leaflet Map | Map showing nearby POIs | App Frontend | P0 | AUTO | Playwright: verify map renders | React-Leaflet MapContainer working |  | 100%
Nearby | Map | Carto Voyager Tiles | Warm, MapQuest-like colors | App Frontend | P0 | MANUAL | Manual: verify tile appearance | Warm MapQuest-like colors, accessible |  | 100%
Nearby | Map | Numbered Markers | Purple circles with numbers | App Frontend | P0 | AUTO | Playwright: verify numbers | SVG-based with dynamic creation |  | 100%
Nearby | Map | Current POI Marker | Gold/yellow circle for current | App Frontend | P0 | AUTO | Playwright: verify gold marker | Gold/yellow circle (#F4C542) with white center |  | 100%
Nearby | Map | Auto-fit Bounds | Zoom to show all markers | App Frontend | P0 | AUTO | Playwright: verify bounds | Radius-based zoom levels with padding |  | 95%
Nearby | Map | Marker Click Highlight | Click marker to highlight card | App Frontend | P0 | AUTO | Playwright: click, verify highlight | Click marker → highlight card, 3s timeout |  | 100%
Nearby | Map | Card Click Pan | Click card to highlight marker | App Frontend | P0 | AUTO | Playwright: click card | Click card → highlight marker |  | 100%
Nearby | Cards | NearbyCard Component | Individual POI card in list | App Frontend | P0 | AUTO | Playwright: verify elements | Distance, hours, amenities, action buttons |  | 100%
Nearby | Cards | Distance Display | Show miles from current POI | App Frontend | P0 | AUTO | Playwright: verify distance | Miles or feet based on distance |  | 100%
Nearby | Cards | Hours Display | Show hours for selected date | App Frontend | P0 | AUTO | Playwright: verify hours | Shows hours but no (Modified) override labels |  | 75%
Nearby | Cards | Category Display | Show primary category | App Frontend | P0 | AUTO | Playwright: verify category | Primary category shown |  | 100%
Nearby | Cards | Amenity Icons | Restrooms, wheelchair, WiFi, pets | App Frontend | P0 | AUTO | Playwright: verify icons | Restrooms, wheelchair, WiFi, pet-friendly icons |  | 100%
Nearby | Cards | Trail Info | Length and difficulty for trails | App Frontend | P0 | AUTO | Playwright: verify length/difficulty | Length + difficulty rating displayed |  | 100%
Nearby | Cards | Event Info | Date for events | App Frontend | P0 | AUTO | Playwright: verify date | Event date displayed |  | 100%
Nearby | Cards | Park Info | Park type for parks | App Frontend | P0 | AUTO | Playwright: verify type | Park type displayed |  | 100%
Nearby | Actions | Directions Modal | Choose navigation app | App Frontend | P0 | AUTO | Playwright: click, verify modal | NN-31: Works but styling needs updates |  | 90%
Nearby | Actions | Google Maps Link | Open in Google Maps | App Frontend | P0 | AUTO | Playwright: verify URL format | Opens with correct coordinates |  | 100%
Nearby | Actions | Apple Maps Link | Open in Apple Maps | App Frontend | P0 | AUTO | Playwright: verify URL format | Working |  | 100%
Nearby | Actions | Waze Link | Open in Waze | App Frontend | P0 | AUTO | Playwright: verify URL format | Working |  | 100%
Nearby | Actions | Copy Address | Copy address to clipboard | App Frontend | P0 | AUTO | Playwright: click, verify full address | Only copying city, not full address |  | 0%
Nearby | Actions | Copy Lat/Long | Copy coordinates to clipboard | App Frontend | P0 | AUTO | Playwright: click, verify clipboard | Fixed - was showing null, now uses front_door coords |  | 100%
Nearby | Pagination | Page Navigation | Next/previous page buttons | App Frontend | P0 | AUTO | Playwright: click next | Next/prev with page numbers |  | 100%
Nearby | Pagination | Items Per Page | 6 items per page default | App Frontend | P0 | AUTO | Playwright: count items | 6 items default |  | 100%
Nearby | Mobile | Touch Targets | 44px+ for accessibility | App Frontend | P0 | MANUAL | Manual: verify 44px+ on mobile | 44px+ WCAG compliant |  | 100%
Nearby | Mobile | Horizontal Scroll Pills | Swipe filter buttons | App Frontend | P0 | MANUAL | Manual: test swipe on mobile | Swipe on mobile with hidden scrollbar |  | 100%
Nearby | Mobile | Icon-only Mode | Icons without text on small screens | App Frontend | P0 | AUTO | Playwright: resize <480px | Icons only on <480px screens |  | 100%
Nearby | Mobile | Responsive Breakpoints | 768px, 480px, 360px | App Frontend | P0 | AUTO | Playwright: resize, verify layout | 768px, 480px, 360px handled |  | 100%
Detail Pages | Routing | Smart Router | POIDetail.jsx dispatches to type-specific | App Frontend | P0 | AUTO | Playwright: navigate, verify component | POIDetail.jsx dispatches to type-specific components |  | 100%
Detail Pages | Routing | Slug-based URLs | /places/, /parks/, /trails/, /events/ | App Frontend | P0 | AUTO | Playwright: verify URL pattern | /places/, /parks/, /trails/, /events/ working |  | 100%
Detail Pages | Routing | UUID Fallback | /poi/{uuid} redirects to slug URL | App Frontend | P0 | AUTO | Playwright: navigate UUID, verify redirect | Client-side redirect via history.replaceState, not HTTP 301 |  | 85%
Detail Pages | Business | BusinessDetail Page | Full business detail view | App Frontend | P0 | HYBRID | Playwright: sections ¦ Manual: design | Comprehensive - price, hours, amenities, menu, contact |  | 90%
Detail Pages | Business | Price Range Display | $, $$, $$$ indicator | App Frontend | P0 | AUTO | Playwright: verify price shown | $/$$/$$$ indicator working |  | 100%
Detail Pages | Business | Business Hours | Show weekly hours with toggle | App Frontend | P0 | AUTO | Playwright: verify hours section | Shows hours but toggle broken (NN-36) |  | 80%
Detail Pages | Business | Contact Info | Phone, email, website | App Frontend | P0 | AUTO | Playwright: verify phone/email/website | Phone, email, website displayed |  | 100%
Detail Pages | Business | Social Links | Instagram, Facebook, X, etc. | App Frontend | P0 | AUTO | Playwright: verify icons/links | All platforms with icons |  | 100%
Detail Pages | Park | ParkDetail Page | Full park detail view | App Frontend | P0 | HYBRID | Playwright: sections ¦ Manual: design | Hours, parking, playground. Missing hunting/fishing |  | 85%
Detail Pages | Park | Park Type Display | State park, local park, etc. | App Frontend | P0 | AUTO | Playwright: verify type | State park, local park, etc. |  | 100%
Detail Pages | Park | Facilities List | Playgrounds, pavilions, etc. | App Frontend | P0 | AUTO | Playwright: verify facilities | Displays park facilities |  | 100%
Detail Pages | Trail | TrailDetail Page | Full trail detail view | App Frontend | P0 | HYBRID | Playwright: sections ¦ Manual: design | Excellent - length, difficulty, surfaces, trailhead |  | 92%
Detail Pages | Trail | Length Display | Miles with icon | App Frontend | P0 | AUTO | Playwright: verify length | Miles with icon |  | 100%
Detail Pages | Trail | Difficulty Badge | Easy/Moderate/Hard | App Frontend | P0 | AUTO | Playwright: verify badge | Easy/Moderate/Hard badge |  | 100%
Detail Pages | Trail | Surface Types | Dirt, gravel, paved, etc. | App Frontend | P0 | AUTO | Playwright: verify surfaces | Trail surfaces displayed |  | 100%
Detail Pages | Event | EventDetail Page | Full event detail view | App Frontend | P0 | HYBRID | Playwright: sections ¦ Manual: design | Good but missing vendor info, repeat pattern |  | 88%
Detail Pages | Event | Date/Time Display | Event date and time | App Frontend | P0 | AUTO | Playwright: verify date/time | Event date/time shown |  | 100%
Detail Pages | Event | Status Indicator | Upcoming, happening now, past | App Frontend | P0 | AUTO | Playwright: verify status | Upcoming/happening/past |  | 100%
Detail Pages | Event | Organizer Info | Event organizer details | App Frontend | P0 | AUTO | Playwright: verify organizer | Organizer name displayed |  | 100%
Detail Pages | Event | Ticket Link | Button to buy tickets | App Frontend | P0 | AUTO | Playwright: verify button | Button to buy tickets |  | 100%
Detail Pages | Common | Photo Gallery | Display all POI images | App Frontend | P0 | AUTO | Playwright: verify images | Grid display with first 8 images |  | 100%
Detail Pages | Common | Photo Lightbox | Full-screen image viewer | App Frontend | P0 | AUTO | Playwright: click, verify lightbox | Working but some type pages have broken lightbox |  | 95%
Detail Pages | Common | Directions Button | Open in maps app | App Frontend | P0 | AUTO | Playwright: click, verify maps | Opens Google Maps with coordinates |  | 100%
Detail Pages | Common | Share Button | Share via social/email | App Frontend | P0 | AUTO | Playwright: click, verify menu | NN-38: Only 'Link Copied' showing, other options missing |  | 40%
Detail Pages | Common | Copy Lat/Long | Copy coordinates | App Frontend | P0 | AUTO | Playwright: click, verify clipboard | Fixed - was showing null, now uses front_door coords |  | 100%
Detail Pages | Common | Verified Badge | Show verified status | App Frontend | P0 | AUTO | Playwright: hover, verify popup | NN-48: Badge shows but popup not showing |  | 70%
Detail Pages | Common | Nearby Section | Embedded nearby feature | App Frontend | P0 | AUTO | Playwright: verify section renders | Embedded NearbySection component |  | 100%
Detail Pages | Common | Amenity Display | Icons for facilities | App Frontend | P0 | AUTO | Playwright: verify icons | Icons for facilities working |  | 100%
Maps | Library | React-Leaflet | Leaflet wrapper for React | App Frontend | P0 | AUTO | Playwright: verify map initializes | Fully integrated with MapContainer |  | 100%
Maps | Tiles | Carto Voyager | Warm, colorful map tiles | App Frontend | P0 | MANUAL | Manual: verify tile appearance | Accessible warm color tiles |  | 100%
Maps | Tiles | Parks Green | Parks shown in green | App Frontend | P1 | MANUAL | Manual: verify parks green | NN-50: Not implemented - parks not green on map |  | 0%
Maps | Tiles | Water Blue | Water shown in blue | App Frontend | P1 | MANUAL | Manual: verify water blue | NN-50: Not implemented |  | 0%
Maps | Tiles | County Borders | Show Chatham County border | App Frontend | P2 | MANUAL | Manual: verify borders visible | NN-50: Not implemented |  | 0%
Maps | Markers | Numbered Markers | Purple circles with numbers | App Frontend | P0 | AUTO | Playwright: verify numbers | SVG-based with dynamic creation |  | 100%
Maps | Markers | Current Location | Gold marker for current POI | App Frontend | P0 | AUTO | Playwright: verify gold marker | Gold marker with white center |  | 100%
Maps | Markers | Marker Popups | Info popup on click | App Frontend | P0 | AUTO | Playwright: click, verify popup | NN-28: Need better card list connection |  | 80%
Maps | Interaction | Click to Set Location | Admin map for coordinates | Admin Frontend | P0 | AUTO | Playwright: click, verify coords | Admin LocationMap working |  | 100%
Maps | Interaction | Auto-fit Bounds | Zoom to show all markers | App Frontend | P0 | AUTO | Playwright: verify bounds | Radius-based zoom levels with padding |  | 95%
Maps | Interaction | Zoom Controls | Plus/minus buttons | App Frontend | P0 | AUTO | Playwright: click +/-, verify zoom | Plus/minus buttons working |  | 100%
SEO | Meta Tags | Dynamic Title | Page title from POI name | App Frontend | P0 | AUTO | Playwright: verify <title> | SEO component exists but not used in specialized detail pages |  | 60%
SEO | Meta Tags | Description | Meta description from teaser | App Frontend | P0 | AUTO | Playwright: verify meta description | 'No Ads. No Clutter.' text |  | 100%
SEO | Meta Tags | Canonical URL | Canonical link tag | App Frontend | P0 | AUTO | Playwright: verify canonical link | Implemented in SEO component |  | 100%
SEO | Open Graph | og:title | Title for social shares | App Frontend | P0 | AUTO | Playwright: verify og:title meta | Not used in BusinessDetail, EventDetail, etc. |  | 50%
SEO | Open Graph | og:description | Description for social | App Frontend | P0 | AUTO | Playwright: verify og:description | Not used in specialized pages |  | 50%
SEO | Open Graph | og:image | Image for social preview | App Frontend | P0 | AUTO | Playwright: verify og:image | Not used in specialized pages |  | 50%
SEO | Open Graph | og:type | place/event type | App Frontend | P0 | AUTO | Playwright: verify og:type | Not used in specialized pages |  | 50%
SEO | Twitter | twitter:card | summary_large_image | App Frontend | P0 | AUTO | Playwright: verify twitter:card | In SEO component |  | 60%
SEO | Twitter | twitter:title | Title for Twitter | App Frontend | P0 | AUTO | Playwright: verify twitter:title | In SEO component |  | 60%
SEO | Twitter | twitter:description | Description for Twitter | App Frontend | P0 | AUTO | Playwright: verify twitter:description | In SEO component |  | 60%
SEO | Structured Data | LocalBusiness JSON-LD | Schema.org LocalBusiness | App Frontend | P0 | AUTO | Playwright: parse JSON-LD | Comprehensive schema with hours, geo, amenities |  | 95%
SEO | Structured Data | Event JSON-LD | Schema.org Event | App Frontend | P0 | AUTO | Playwright: parse Event schema | Full Event schema with organizer, offers, location |  | 95%
SEO | Structured Data | GeoCoordinates | Lat/long in structured data | App Frontend | P0 | AUTO | Playwright: verify coords | In structured data |  | 100%
SEO | Structured Data | OpeningHours | Hours in structured data | App Frontend | P1 | AUTO | Playwright: verify hours | In structured data |  | 90%
Sharing | Buttons | Native Share API | Device native share | App Frontend | P0 | MANUAL | Manual: test on mobile | navigator.share working on mobile |  | 100%
Sharing | Buttons | Facebook Share | Share to Facebook | App Frontend | P0 | AUTO | Playwright: verify share URL | Code exists but NN-38: not showing in dropdown |  | 100%
Sharing | Buttons | Twitter Share | Share to Twitter/X | App Frontend | P0 | AUTO | Playwright: verify share URL | Code exists but NN-38: not showing |  | 100%
Sharing | Buttons | Email Share | Share via email | App Frontend | P0 | AUTO | Playwright: verify mailto | mailto: protocol working |  | 100%
Sharing | Buttons | Copy Link | Copy URL to clipboard | App Frontend | P0 | AUTO | Playwright: click, verify clipboard | Clipboard API with fallback |  | 100%
Hours | Regular | Weekly Hours | Day-by-day operating hours | Admin Backend | P0 | AUTO | pytest: save, verify JSONB | JSONB structure with day-by-day hours |  | 100%
Hours | Regular | Open/Close Times | Start and end time per day | Admin Backend | P0 | AUTO | pytest: verify format | Fixed, dawn, dusk, appointment types supported |  | 100%
Hours | Regular | Closed Days | Mark days as closed | Admin Backend | P0 | AUTO | pytest: set closed, verify | Status field per day |  | 100%
Hours | Seasonal | Season Name | Label for season (Summer, Winter) | Admin Backend | P1 | AUTO | pytest: verify names | Spring/Summer/Fall/Winter predefined |  | 100%
Hours | Seasonal | Start Date | Season start date | Admin Backend | P1 | AUTO | pytest: verify MM-DD format | MM-DD format for seasonal |  | 100%
Hours | Seasonal | End Date | Season end date | Admin Backend | P1 | AUTO | pytest: verify MM-DD format | MM-DD format for seasonal |  | 100%
Hours | Seasonal | Seasonal Hours | Hours during season | Admin Backend | P1 | AUTO | pytest: save, verify | Backend complete, frontend partial |  | 90%
Hours | Holiday | Holiday Name | Name of holiday | Admin Backend | P1 | AUTO | pytest: verify names | 20 holidays predefined |  | 100%
Hours | Holiday | Holiday Date | Specific date | Admin Backend | P1 | AUTO | pytest: verify calculation | Calculated with moveable holiday support |  | 100%
Hours | Holiday | Holiday Hours | Hours or closed | Admin Backend | P1 | AUTO | pytest: save, verify | Open/closed/modified statuses |  | 95%
Hours | Exceptions | Recurring Monthly | 3rd Wednesday closed, etc. | Admin Backend | P2 | AUTO | pytest: test 3rd Wednesday | 3rd Wednesday patterns fully working |  | 100%
Hours | Exceptions | Exception Type | Closed, modified hours | Admin Backend | P2 | AUTO | pytest: verify types | Closed or modified |  | 100%
Hours | Exceptions | Exception Override | Override regular hours | Admin Backend | P2 | AUTO | pytest: verify priority | Priority: exceptions > holidays > seasonal > regular |  | 100%
Hours | Frontend | Hours Display Component | HoursDisplay.jsx | App Frontend | P0 | AUTO | Playwright: verify renders | HoursDisplay.jsx working but toggle broken |  | 80%
Hours | Frontend | Open Now Status | Show if currently open | App Frontend | P0 | AUTO | pytest: mock time, verify | isCurrentlyOpen() calculates correctly |  | 95%
Hours | Frontend | Hours Toggle | Expand to see all hours | App Frontend | P0 | AUTO | Playwright: click, verify expand | NN-36: NOT WORKING - user reported |  | 0%
Hours | Frontend | Date-specific Hours | Show hours for selected date | App Frontend | P0 | AUTO | Playwright: pick date | Works but no (Modified) override labels |  | 75%
Hours | Frontend | Override Display | Show modified/holiday indicator | App Frontend | P1 | AUTO | Playwright: verify (Modified) label | NN-36: Not showing (Modified)/(Holiday) indicators |  | 0%
Users | CLI | Create User | manage_users.py create command | Admin Backend | P0 | AUTO | pytest: run CLI, verify DB | manage_users.py create command working |  | 100%
Users | CLI | List Users | manage_users.py list command | Admin Backend | P0 | AUTO | pytest: run CLI, verify output | Formatted table with email, role, created_at |  | 100%
Users | CLI | Delete User | manage_users.py delete command | Admin Backend | P0 | AUTO | pytest: run CLI, verify removed | Working but no confirmation prompt |  | 80%
Users | CLI | Test User | manage_users.py test-user command | Admin Backend | P0 | AUTO | pytest: run CLI, verify created | test@nearbynearby.com / 1234 working |  | 100%
Users | CLI | Role Assignment | --role flag on create | Admin Backend | P0 | AUTO | pytest: create with role | --role flag on create working |  | 100%
Users | API | Create User Endpoint | POST /api/auth/users (Admin) | Admin Backend | P1 | AUTO | pytest: POST /api/auth/users | POST exists but no admin enforcement |  | 50%
Users | Frontend | User Management UI | Admin page to manage users | Admin Frontend | P2 | HYBRID | Playwright: CRUD ¦ Manual: UX | Not implemented - CLI only |  | 0%
Infrastructure | Docker | Dev Compose | docker-compose.yml | Infrastructure | P0 | AUTO | Bash: docker compose up | 5 services: minio, db, backend, frontend, test-db |  | 100%
Infrastructure | Docker | Prod Compose | docker-compose.prod.yml | Infrastructure | P0 | AUTO | Bash: docker compose -f prod | 2 services connecting to RDS |  | 100%
Infrastructure | Docker | Multi-stage Build | Separate build and runtime | Infrastructure | P0 | AUTO | Bash: build, verify size | All Dockerfiles optimized with builder stages |  | 100%
Infrastructure | Docker | Health Checks | Container health monitoring | Infrastructure | P0 | AUTO | Bash: docker inspect | DB/MinIO have checks, dev backend missing |  | 85%
Infrastructure | Docker | Volume Mounts | Persistent data storage | Infrastructure | P0 | AUTO | Bash: verify data persists | Persistent postgres_data, minio_data, image_storage |  | 100%
Infrastructure | Database | PostgreSQL 15 | Main database server | Infrastructure | P0 | AUTO | pytest: verify PG version | Running with extensions |  | 100%
Infrastructure | Database | PostGIS 3.4 | Geospatial extension | Infrastructure | P0 | AUTO | pytest: SELECT PostGIS_Version() | Extension enabled and working |  | 100%
Infrastructure | Database | Alembic Migrations | Schema version control | Infrastructure | P0 | AUTO | Bash: alembic upgrade head | 25 migrations, some merged heads |  | 95%
Infrastructure | Database | Connection Pooling | SQLAlchemy pool config | Infrastructure | P0 | AUTO | pytest: verify pool config | SQLAlchemy pool configured |  | 100%
Infrastructure | Storage | AWS S3 | Production image storage | Infrastructure | P0 | AUTO | pytest: upload/download S3 | Production storage working |  | 100%
Infrastructure | Storage | MinIO | Development S3 compatibility | Infrastructure | P0 | AUTO | pytest: upload/download MinIO | Dev S3-compatible with auto-bucket |  | 100%
Infrastructure | Storage | CloudFront CDN | Image delivery optimization | Infrastructure | P2 | AUTO | pytest: verify CDN URL | Not configured yet |  | 0%
Infrastructure | CI/CD | GitHub Actions | Automated pipeline | Infrastructure | P0 | AUTO | GH Actions: verify workflow | CI/CD pipeline with OIDC |  | 100%
Infrastructure | CI/CD | ECR Push | Push images to AWS ECR | Infrastructure | P0 | AUTO | GH Actions: verify image | Docker image push working |  | 100%
Infrastructure | CI/CD | ECS Deploy | Deploy to AWS ECS | Infrastructure | P0 | AUTO | GH Actions: verify deployment | Force new deployment working |  | 100%
Infrastructure | Network | Docker Network | nearby-admin_default network | Infrastructure | P0 | AUTO | Bash: docker network inspect | nearby-admin_default, DNS collision documented |  | 95%
Infrastructure | Network | DNS Resolution | Container name resolution | Infrastructure | P0 | AUTO | Bash: nslookup from container | Workaround with explicit container names |  | 90%
Infrastructure | Network | CORS Config | Cross-origin settings | Infrastructure | P0 | AUTO | pytest: verify CORS headers | Configured for allowed origins |  | 100%
Database | Tables | points_of_interest | Main POI table (140+ fields) | Database | P0 | AUTO | pytest: verify schema | 140+ fields main table |  | 100%
Database | Tables | businesses | Business subtype table | Database | P0 | AUTO | pytest: verify schema | 25+ columns subtype |  | 100%
Database | Tables | parks | Park subtype table | Database | P0 | AUTO | pytest: verify schema | 18+ columns subtype |  | 100%
Database | Tables | trails | Trail subtype table | Database | P0 | AUTO | pytest: verify schema | 20+ columns subtype |  | 100%
Database | Tables | events | Event subtype table | Database | P0 | AUTO | pytest: verify schema | 22+ columns subtype |  | 100%
Database | Tables | categories | Category table (hierarchical) | Database | P0 | AUTO | pytest: verify schema | Hierarchical with parent_id |  | 100%
Database | Tables | poi_category_association | POI-category junction | Database | P0 | AUTO | pytest: verify junction | Junction with is_main flag |  | 100%
Database | Tables | images | Image metadata table | Database | P0 | AUTO | pytest: verify schema | S3 metadata with variants |  | 100%
Database | Tables | attributes | Dynamic attribute definitions | Database | P0 | AUTO | pytest: verify schema | Dynamic attribute definitions |  | 100%
Database | Tables | poi_relationships | POI-to-POI links | Database | P0 | AUTO | pytest: verify schema | Composite PK relationship table |  | 100%
Database | Tables | users | Admin users table | Database | P0 | AUTO | pytest: verify schema | With bcrypt hashed passwords |  | 100%
Database | Tables | primary_types | POI primary types | Database | P0 | AUTO | pytest: verify schema | POI primary type reference |  | 100%
Database | Tables | waitlist | Email waitlist | Database | P1 | AUTO | pytest: verify schema | Email collection table |  | 100%
Database | Indexes | Trigram Index (name) | GIN index for fuzzy search | Database | P0 | AUTO | pytest: verify index | GIN index on name for fuzzy search |  | 100%
Database | Indexes | Trigram Index (city) | GIN index for city search | Database | P0 | AUTO | pytest: verify index | Documented, may need manual creation |  | 90%
Database | Indexes | Geospatial Index | GIST index on location | Database | P0 | AUTO | pytest: verify GIST | GIST index on location column |  | 100%
Database | Indexes | Vector Index | IVFFlat on embedding column | Database | P0 | AUTO | pytest: verify IVFFlat (prod) | IVFFlat on prod, not local dev |  | 65%
Database | Indexes | Status Index | Index on publication_status | Database | P0 | AUTO | pytest: verify index | Index on publication_status |  | 100%
Database | Extensions | pg_trgm | Trigram text search | Database | P0 | AUTO | pytest: verify extension | Extension enabled |  | 100%
Database | Extensions | pgvector | Vector similarity search | Database | P0 | AUTO | pytest: verify extension (prod) | Prod yes, local dev no |  | 65%
Database | Extensions | PostGIS | Geospatial functions | Database | P0 | AUTO | pytest: verify extension | Extension enabled with geometry functions |  | 100%
Explore | Layout | Category Grid | 4 category cards with icons | App Frontend | P0 | AUTO | Playwright: verify 4 cards | 4 categories with lucide-react icons |  | 100%
Explore | Layout | Live Counts | Show POI count per category | App Frontend | P0 | AUTO | Playwright: verify counts | Real-time API calls per category |  | 100%
Explore | Layout | Split View | List on left, map on right | App Frontend | P0 | AUTO | Playwright: verify layout | List left, map right layout |  | 100%
Explore | Filtering | Type Filter | Filter by POI type | App Frontend | P0 | AUTO | Playwright: click, verify filter | URL parameter ?type=BUSINESS |  | 100%
Explore | Filtering | Search Within | Search filtered results | App Frontend | P0 | AUTO | Playwright: search, verify | Real-time name filtering |  | 100%
Explore | Filtering | Distance Sort | Sort by distance from location | App Frontend | P1 | AUTO | Playwright: verify order | Haversine formula calculation |  | 100%
Explore | Features | Save/Favorites | Save POIs to list | App Frontend | P2 | AUTO | Playwright: click heart | Placeholder 'coming soon' alert only |  | 5%
Homepage | Hero | Main Tagline | 'What's Actually Nearby' | App Frontend | P0 | AUTO | Playwright: verify text | 'What's Actually Nearby' displayed |  | 100%
Homepage | Hero | Search Bar | Central search input | App Frontend | P0 | AUTO | Playwright: verify input | Central SearchBar component |  | 100%
Homepage | Hero | Announcement Bar | Testing location notice | App Frontend | P0 | AUTO | Playwright: verify text | Pittsboro, NC testing notice |  | 100%
Homepage | Hero | Description | 'No Ads. No Clutter.' | App Frontend | P0 | AUTO | Playwright: verify meta description | 'No Ads. No Clutter.' text |  | 100%
Homepage | Sections | Feature Showcase | Platform features display | App Frontend | P1 | HYBRID | Playwright: sections ¦ Manual: content | 3-step SimpleSection guide |  | 100%
Homepage | Sections | Signup Bar | Email waitlist signup | App Frontend | P0 | AUTO | Playwright: submit, verify API | Email collection to /api/waitlist |  | 95%
Homepage | Sections | Info Sections | Additional info blocks | App Frontend | P1 | HYBRID | Playwright: expand ¦ Manual: content | 6 FAQ questions in InfoSection |  | 100%
Homepage | Navigation | Navbar | Top navigation bar | App Frontend | P0 | AUTO | Playwright: verify links | Top navigation working |  | 100%
Homepage | Navigation | Footer | Site footer with links | App Frontend | P0 | AUTO | Playwright: verify links | Social links, CTA. Sponsors hidden |  | 90%
Known Issues | NN-55 | POI Update HTTP 422 | Error when updating POI | Admin Backend | P0 | AUTO | pytest: reproduce, verify fix | UNRESOLVED - Schema validation too strict |  | 0%
Known Issues | NN-4 | Can't Save New POIs | HTTP 500 on save | Admin Backend | P0 | AUTO | pytest: create POI | CRITICAL - HTTP 500, intermittent |  | 0%
Known Issues | NN-38 | Map Zoom Too Far | Default zoom needs adjustment | Admin Frontend | P1 | MANUAL | Manual: verify zoom appropriate | Improved but needs more tuning |  | 70%
Known Issues | NN-38 | Address Autocomplete | Need address suggestions | Admin Frontend | P2 | AUTO | Playwright: type, verify suggestions | NOT IMPLEMENTED |  | 0%
Known Issues | NN-36 | Seasonal Date Ranges | Can't specify season dates | Admin Backend | P1 | AUTO | pytest: verify saves | IMPLEMENTED in HoursSelector |  | 100%
Known Issues | NN-36 | Recurring Exceptions | Monthly patterns not supported | Admin Backend | P2 | AUTO | pytest: verify patterns | IMPLEMENTED - 3rd Wednesday patterns work |  | 100%
Known Issues | NN-36 | Hours Toggle Frontend | Toggle button not working | App Frontend | P0 | AUTO | Playwright: click toggle | NOT WORKING - toggle broken |  | 0%
Known Issues | NN-46 | Venue Data Inheritance | Events don't pull from venue | Admin Backend | P1 | AUTO | pytest: verify venue data | NOT IMPLEMENTED |  | 0%
Known Issues | NN-46 | Events Page Blank | Events list showing blank | App Frontend | P0 | AUTO | Playwright: navigate, verify renders | CRITICAL - White screen |  | 0%
Known Issues | NN-50 | Map Colors A11y | Color contrast issues | App Frontend | P1 | MANUAL | Manual: colorblind simulation | FIXED - Carto Voyager accessible tiles |  | 100%
Known Issues | NN-57 | Teaser Char Limit | Need 120 char limit | Admin Frontend | P0 | AUTO | Playwright: type >120 | No character counter in UI |  | 0%
Known Issues | NN-57 | Parking Lat/Long | Missing parking coordinates | Admin Backend | P1 | AUTO | pytest: verify fields | MISSING field |  | 0%
Known Issues | NN-57 | Restroom Duplicate | Can't add multiple restrooms | Admin Frontend | P1 | AUTO | Playwright: click add | Parks only, need for Trails/Events |  | 50%
Known Issues | NN-57 | Playground Lat/Long | Missing playground coordinates | Admin Backend | P1 | AUTO | pytest: verify fields | MISSING field |  | 0%
Known Issues | NN-57 | Corporate Checkboxes | Checkboxes not clickable | Admin Frontend | P0 | AUTO | Playwright: click, verify state | NOT CLICKABLE - Radio.Group issue |  | 0%
Known Issues | NN-48 | Verified Badge Popup | Popup not showing | App Frontend | P0 | AUTO | Playwright: hover, verify popup | NOT SHOWING on hover |  | 0%
Known Issues | NN-38 | Share Options | Only copy link showing | App Frontend | P0 | AUTO | Playwright: click, verify options | Only copy link showing |  | 0%
Known Issues | NN-31 | Copy Address | Only copying city | App Frontend | P0 | AUTO | Playwright: click, verify full address | Only copying city, not full address |  | 0%
Known Issues | NN-28 | Map Marker Connection | Connect markers to card list | App Frontend | P1 | AUTO | Playwright: click, verify scroll | Works but could be better UX |  | 80%